## Release Details
FMS Global release checklist
Dec 12th, 2020 |  |  | Database Details
|  |  | Source | GBFUDEV1
SDM # | CHG0198107 |  | Target | GBFPROD
|  |  | Backout | File Backup(Fix), CAPI(DC)
Change window
Start Time | 2020-12-12 08:30 | IST | Contact Details
End Time | 2020-12-12 22:30 | IST | Production Support
Duration | 14 | Hours
|  |  | Durga | +91 9035276827
Critical Activities |  |  | Madhav
Hold Batch | Yes |  | Delivery
Bounce Servers | Yes |  | Salman | +91 8015598501
Run Audits | Yes |  | Sweta | +91 9886764416
DB R/W Access | No |  | Nazeer | +91 9902439729
Created by | Salman/Nazeer
Reviewed by | Nikhil
Stakeholder list for communication

## Forward Steps
FMS Global release Checklist - CHG0198107
Forward Steps
RELEASE IMPLEMENTATION PRE-WORK
Double check these activities |  | Durga
Ensure there is an CO for the release and it has been approved
Ensure that the uppercase ids are unlocked in the following environments | GBFPROD
GBFUDEV1
Notify CMS team to hold Saturday batch jobs in Global Production |  | Salman/Nazeer
RUN AUDITS - Pre
Run audit reports ( DDDAUDIT and SYSAUDIT) to ensure that your target database is clean
Copy audit reports to the "D:\CHG0198107\Before" directory
PERFORM MIGRATION
Setup Environment, follow steps given in the Word Doc attached. |  | Durga
Migrate the Project definition only ANZAUFMS201212_S2P from GBFUDEV1 to GBFPROD
Copy Project ANZAUFMS201212_S2P from GBFPROD to file
Please follow attached mail for CAPI Release Migration ( Manadatory Step) | Should be select Rollback and Migration Check boxes on Release Definition page.
Migrate the Release AUFMS201212_S2P via CAPI (Source GBFUDEV1)
Save the project as SCRAP_ANZAUFMS201212_S2P in GBFPROD and compare it with GBFUDEV1
Check and copy the log files to the "D:\CHG0198107\Logs" directory
Manual Instruction Steps
Perform manual steps as in doc attached alongside. |  | Durga
Run Portal security sync process |  | Durga
Clear Production App server Cache |  | Durga
RUN AUDITS - Post
Run audit reports ( DDDAUDIT and SYSAUDIT) to ensure that your target database is clean |  | Durga
Copy audit reports to the "D:\CHG0198107\After" directory
VERIFICATION
Zip all the contents of the folder D:\CHG0192288\ and attach it on the SDM |  | ERP Delivery Team
Migration is complete. Technical verification to be done by ERP Delivery team
Send Email to CMS team to release Saturday batch jobs which were kept on hold |  | Salman/Nazeer

## Backout Steps
FMS Global release checklist - CHG0198107
Backout Steps
PERFORM MIGRATION
RollBack the release AUFMS201212_S2P by CR | Durga
Copy project from file which was created in step 17 in forward migration
Save the project as SCRAP_ANZAUFMS201212_S2P in GBFPROD and compare it with file (Forward Steps 17 row)
Check and copy the log files to the "D:\CHG0198107\Backout\Logs" directory
SQR - Rollback
Copy anz0665e.sqr and anz0665a.sqc from backup into D:\psoft\cust_app\GBFPROD\sqr_anz | Aqief/Durga
RUN AUDITS
Run audit reports ( DDDAUDIT and SYSAUDIT) to ensure that your target database is clean | Durga
Copy audit reports to the "D:\CHG0198107\Before" directory
Backout Steps
Perform backout steps as in doc attached alongside. | Durga
VERIFICATION
Zip all the contents of the folder D:\CHG0198107\ and attach it on the SDM | ERP Delivery Team
Backout is complete. Technical verification to be done by ERP Delivery team
Send Email to CMS team to release Saturday batch jobs which were kept on hold | Salman/Nazeer

## Instructions
Miscellaneous Instructions
Project Build Settings
Use the below Build settings while building the project
Create Tab
| Table Creation options | Skip table if it already exists
| View creation options | Skip view if it already exists
| Index creation options | Recreate index if it already exists
Alter Tab
| Drop Column Options | Drop column if data present
| Change column length options | Truncate data if field too short
| Alter Any | Check all the check boxes
| Alter even if not changes | Uncheck
| Alter table options | Alter by table rename
File Locations
File Type | Extension | Location
ASP Page Files | .asp | src\cbl\base\
COBOL | .cbl | src\cbl\base\
COBOL Compiled | .gnt | CBLbin\
COBOL DMS Scripts | .dms | src\cbl\base\
Crystal Reports | .RPT | crw\eng\
DMS .DAT Files | .dat | anz_scripts\
Excel Addins | .xla | EXCEL\
Excel Spreadsheets | .xls | EXCEL\
nVision Drill Downs | .xnv | Nvision\layout\drilldown
nVision Layouts | .XNV | Nvision\layout\
SQC | .sqc | sqr\
SQR | .sqr | sqr\
Visual Basic Script | .vbs | anz_scripts\
Process Run
Name | Process Name | Navigation | Run Control | Parameters
Sysaudit | SYSAUDIT | PeopleTools> Process scheduler> System process requests | Add IFRS_LA# as the run control ID | No parameters required
DDDAudit | DDDAUDIT | PeopleTools> Process scheduler> System process requests | Add IFRS_LA# as the run control ID | No parameters required
Portal Security sync | PORTAL_CSS | PeopleTools> Portal> Portal security sync | Add IFRS_LA# as the run control ID | Portal Name - EMPLOYEE Delete Invalid security - Check
Query access list cache | PSQRYACCLIST | PeopleTools>Security>Query Security> Query access list cache | Add IFRS_LA# as the run control ID | Select Enable access cache list
Syncronize collection security | PTPP_SCSYNC | PeopleTools>Portal>Portal utilities>Sync collection security | Add IFRS_LA# as the run control ID | Portal Name - EMPLOYEE Collection Name - Blank
Version control | VERSION | PeopleTools> Application Engine> Request AE | Add IFRS_LA# as the run control ID | Process Frequency - Once