## Slide 1: PeopleSoft Automation
Participants : Sameer Khanna, Kathy Kha, Sidhant Dayal, Vineet Wadwekar, Shivangi Tyagi, Venkat P, Karthik R, Sourav Mitra, Shyam Jha, Ramesh N, Bhanu M and Jatin P.

## Slide 2
PeopleSoft HCM

## Slide 3
Summary – Regression Suite
Total Regression Test Cases
. Automated : 317
. Manual : 175
Progression Automation for
Corp X PI XI Sprint 1
. Total Tests : 40
. Reused existing automated tests : - 7
. Automated/Automatable : 2/2
Team Commentary
Achievements from the past fortnight
ST for Sprint 1 stands at 60% completion.
Comment on Summary – Regression Suite section
.Regression Testing for the last Sprint has been completed, progression testing is in progress. We have planed to run the 40 regression test scripts for the current Sprint-1 on 01-04-2021, which includes the test scripts related to ADMIN and MSS.
Comment on the Test Execution Plan vs Actual variance
. N/A
Actions & Support
Support Needed
No open incidents or requests
Actions from previous meeting
N/A
Executive Summary for Core HR
Current area of focus:
System testing is currently underway. We used existing PTF scripts to create test data for current sprint, as most of the testing involved Mail Notification testing, Report testing including change in page functionality for already available PTF scripts.
Current status of the focus area: Green/Amber/Red
GREEN
Chart: 
| GL-AU | GL-NZ | GL-UK | GL-SG | GL-HK | GL-CH | GL-FJ | AM-AU | AM-NZ | AM-CH
Script/Data
Functional Defect
Environment
Chart: 
| 44272 | 44273 | 44274 | 44277 | 44278 | 44279 | 44280 | 44281 | 44284 | 44285 | 44286
Planned Test Execution
Actual Test Execution
Column1
Column2
Column3
Column4
Team
Jatin (Presenter)
John
From Core HR
Date: 12 Apr 2021

## Slide 4
PeopleSoft Core Finance- GL | AM |LA

## Slide 5
Summary – Regression Suite
Total Regression Test Cases
. Automated : 831
. Manual: 112
Progression Automation for
Corp X PI XI Sprint 1
. Total Tests : 41
. Reused existing automated tests : 0
. Automated/Automatable : 28/28
Team Commentary
Achievements from the past fortnight
ST completed for China, ST for Global stands at 99% completion
Comment on Summary – Regression Suite section
.13 tests were run manually which include Excel loaders and Config checks.
Comment on the Test Execution Plan vs Actual variance
. Minor variance due to time for defect resolution and retesting.
Comment on the defect distribution numbers
. There is only 1 outstanding defects
.
Actions & Support
Support Needed
No open incidents or requests
Actions from previous meeting
Balance Compare Load issue
China Online Journal Edit performance
Executive Summary for GL, AM & LA
Current area of focus: PeopleTools upgrade + GL selective adoption initiative.
System testing cycle 2 is currently underway. Cycle 1 has been completed on a lower version of tools and now closed. Cycle 2 testing is 99% complete except for 10 outstanding test cases which are expected to be done and Cycle 3 is expected to commence by 13th Apr.
Current status of the focus area: Green/Amber/Red
GREEN
Chart: 
| GL-AU | GL-NZ | GL-UK | GL-SG | GL-HK | GL-CH | GL-FJ | AM-AU | AM-NZ | AM-CH
Script/Data | 8 | 16 | 17 | 13 | 16 | 18 | 1 | 1 | 0 | 12
Functional Defect | 5 | 2 | 1 | 0 | 1 | 7 | 0 | 0 | 0 | 7
Environment | 15 | 0 | 1 | 0 | 0 | 3 | 0 | 2 | 2 | 0
Chart: 
| 44232 | 44246 | 44260 | 44274 | 44288 | 44302 | 44316
Planned Test Execution | 0 | 63 | 397 | 672 | 816 | 943
Actual Test Execution | 0 | 57 | 232 | 684 | 787 | 933
Column1
Column2
Column3
Column4
Team
Navneet (Presenter)
Ramesh
Santosh
Vishnu
Kiran
Harika
From Evolve & Protect
Date: 12 April 2021

## Slide 6
Chart: 
| 44127 | 44141 | 44155 | 44169 | 44183 | 44196
Planned Test Execution | 0 | 209 | 579 | 776
Actual Test Execution | 0 | 147 | 295 | 499 | 761 | 770
Column1
Column2
Column3
Column4
Chart: 
| GL-AU | GL-NZ | GL-UK | GL-SG | GL-HK | GL-FJ | GL-CH | AM-NZ | AM-UK | AM-CH
Script/Data | 30 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 11 | 5
Functional Defect | 17 | 2 | 2 | 3 | 2 | 1 | 5 | 2 | 1 | 1
Environments | 5 | 0 | 0 | 0 | 0 | 5 | 1 | 1 | 1 | 1

## Slide 7: Cycle 2 Execution Summary for PS GL/AM/LA
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 12th Apr | Pass | Fail | Not Executed | Defect Resolved | ETA
GL | 11 Apr 2021 | 422 | 42 | 464 | 464 | 463 | 1 | 0 | 45 out of 46 | 1 failure is for long running Jedit in China which is in progress.
AM | 11 Apr 2021 | 238 | 70 | 308 | 308 | 308 | 0 | 0 | 17 out of 17 | 
LA | 11 Apr 2021 | 171 | 0 | 171 | 161 | 161 | 0 | 0 | 7 out of 7 | ETA is 14th Apr

## Slide 8: Projection for Next 2 weeks – GL/AM/LA
Country | Module | Category | Coverage | Test Cycle | Assignee | Activity | Planned Start Date | Planned End Date | Test Cases
CHN | AM | Automated | Regression | Cycle 3 | Ramesh | Execution | 12-Apr-21 | 15-Apr-21 | 34
CHN | AM | Manual | Regression | Cycle 3 | Ramesh | Execution | 16-Apr-21 | 20-Apr-21 | 14
CHN | AM | Automated | Progression | Cycle 3 | Navneet | Execution | 14-Apr-21 | 15-Apr-21 | 6
CHN | AM | Manual | Progression | Cycle 3 | Navneet | Execution | 16-Apr-21 | 20-Apr-21 | 12
AUS | AM | Automated | Regression | Cycle 3 | Ramesh | Execution | 21-Apr-21 | 23-Apr-21 | 35
AUS | AM | Automated | Progression | Cycle 3 | Navneet | Execution | 21-Apr-21 | 22-Apr-21 | 6
AUS | AM | Manual | Progression | Cycle 3 | Navneet | Execution | 22-Apr-21 | 23-Apr-21 | 6
CHN | GL | Automated | Regression | Cycle 3 | Vishnu | Execution | 12-Apr-21 | 16-Apr-21 | 75
CHN | GL | Manual | Regression | Cycle 3 | Vishnu | Execution | 16-Apr-21 | 20-Apr-21 | 17
GBL | Archival | Manual | Regression | Cycle 3 | Simadri/ | Execution | 12-Apr-21 | 23-Apr-21 | 22
CHN | LA | Automated | Regression | Cycle 3 | Santosh | Execution | 14-Apr-21 | 21-Apr-21 | 28
AUS | GL | Automated | Regression | Cycle 3 | Vishnu | Execution | 21-Apr-21 | 23-Apr-21 | 82

## Slide 9: Blocker & Environment issue – GL/AM/LA
Sl No | Backlog / Issue | Raised On | Owner | Status | Aging | Comment
2 | INC3268563 – Long running Online Journal Edit in China | 14th Dec 21 | Kiran | Open | 73 | Build completed for EOD update changes, Unit test is in progress.

## Slide 10: Cycle 1 Execution Summary for PS GL
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 31st Mar | Pass | Fail | Not Executed | Defect Resolved | ETA
GL - Cycle 1 | 25 Dec 2020 | 422 | 34 | 456 | 451 | 451 | 0 | 5 | 42 out of 42 | Completed except for 5 Manual Test cases related archival are deferred to Cycle 3 (ETA 11thh Apr) and 1 failed test case.
AM –Cycle 1 | 25 Dec 2020 | 238 | 18 | 256 | 256 | 256 | 0 | 0 | 3 out of 3 | Completed.
LA –Cycle 1 | 25 Dec 2020 | 78 | 0 | 78 | 78 | 78 | 0 | 0 | 0 | Completed.

## Slide 11
Source to Pay (S2P)

## Slide 12
Summary – Regression Suite
Total Regression Test Cases
. Automated (AP/Purchasing/E-Proc) : 419 & 95 & 44(Total of 558)
. Manual(AP/Purchasing): 29 & 4(Total of 33)
Progression Automation for
Corp X PI XI Sprint 2
. Total Tests : 31
. Reused existing automated tests : - 3
. Automated/Automatable : 12/12
Team Commentary
Achievements from the past fortnight
. Completed AP test execution for Taiwan; Manual scenarios execution got completed including the re-testing of 10 scenarios. China Scripts got executed in CNFUSYS1 except the scenarios which needs to be re-tested.
Comment on Summary – Regression Suite section
. AP Taiwan batch execution Completed.
Comment on the Test Execution Plan vs Actual variance
. As per the Plan, we have completed AP module execution for Taiwan
Comment on the defect distribution numbers
.PR/Voucher approval users list page issue is fixed now and retest under progress.
The execution details for cycle 1 (now closed) is available on the last slide.
Actions & Support
Support Needed
. CNFUSYS1 with latest refresh of PROD.
.PIA Access issue specific to few roles.
.Voucher/PR approver page issue is fixed. Currently, retesting is in progress.
China Voucher save SQL issue and Report manager issue are fixed and re-testing is in progress.
Executive Summary for Bhanu
Current area of focus: People Tools upgrade + GL selective adoption initiative.
System testing cycle 2 is currently underway. Cycle 1 has been completed on a lower version of tools and now closed. Cycle 2 testing is currently in progress is planned to complete on 12th April 2021.
Current status of the focus area: Green/Amber/Red
Green
Chart: 
| Thailand | UK | Taiwan | China
Script/Data | 0 | 0 | 9 | 0
Functional Defect | 1 | 1 | 0 | 1
Environment | 0 | 0 | 0 | 0
Intermittent Issue | 0 | 0 | 0 | 0
Chart: 
| 44286 | 44287 | 44288 | 44291 | 44292 | 44293 | 44294 | 44295
Planned Test Execution | 0 | 9 | 6 | 27 | 0 | 6 | 15 | 18
Actual Test Execution | 6 | 19 | 16 | 6 | 18 | 9 | 27 | 4
Column1
Column2
Column3
Column4
Team
Bhanu (Presenter)
Aishwarya
Swati
Nazeer
Kritika
From S2P Squad
Date: 31 March 2021

## Slide 13
Chart: 
| 23 Oct - AU | 30 Oct - AU | 6 Nov - NZL | 13 Nov - NZL | 20 Nov - SGP | 27 Nov - JPN | 4 Dec - TWN | 8 Dec - LAOS | 11 Dec - IND | 18 Dec - VNM | 25 Dec - CHN | 31 Dec - CHN
Planned Test Execution | 20 | 21 | 39 | 39 | 41 | 41 | 40 | 41 | 85 | 40 | 17 | 18
Actual Test Execution | 18 | 23 | 38 | 40 | 38 | 41 | 39 | 36 | 83 | 40 | 15 | 18
Column1
Column2
Column3
Column4
Chart: 
| AP | PUR | E-PROC
Functional/Scripts | 1 | 0 | 0
Environment | 0 | 0 | 0
Intermittent | 0 | 0 | 0
Build issue | 1 | 0 | 0

## Slide 14: Cycle 2 Execution Summary for S2P
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 17th Mar | Pass | Fail | Not Executed | Defect Resolved | ETA
Purchasing-Cycle2 | 5 Mar 2021 | 95 | 0 | 95 | 95 | 95 | 0 | 0 | 0 | Completed
E-Proc-Cycle2 | 11 Apr 2021 | 44 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | Completed(Note: Requisition approval workflow is considered for next PI as there are design-changes)
AP-Cycle2 | 11 Apr 2021 | 419 | 29 | 448 | 448 | 442 | 6 | 0 | 2 of 3 | Taiwan execution is completed successfully. In China execution , Even after refresh, we identified report manager issue and voucher save level SQL error in China execution. Currently, we are re-testing it.

## Slide 15: Execution Tracker for S2P
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
IND | Purchasing | Automation | Regression | Cycle 2 | Bhanu | Data Input | 8-Mar-21 | 8-Mar-21 | 8-Mar-21 | 8-Mar-21
 |  |  |  |  |  | Batch | 9-Mar-21 | 9-Mar-21 | 9-Mar-21 | 9-Mar-21
 |  |  |  |  |  | Verification | 10-Mar-21 | 10-Mar-21 | 10-Mar-21 | 10-Mar-21
 |  |  |  |  |  | Re-run | 11-Mar-21 | 11-Mar-21 | 11-Mar-21 | 11-Mar-21
IND | AP | Automation | Regression | Cycle 2 | Aishwarya | Data Input | 12-Mar-21 | 12-Mar-21 | 12-Mar-21 | 12-Mar-21
 |  |  |  |  |  | Batch | 15-Mar-21 | 15-Mar-21 | 15-Mar-21 | 15-Mar-21
 |  |  |  |  |  | Verification | 16-Mar-21 | 16-Mar-21 | 16-Mar-21 | 16-Mar-21
 |  |  |  |  |  | Re-run | 17-Mar-21 | 17-Mar-21 | 16-Mar-21 | 16-Mar-21
JPN | AP | Automation | Regression | Cycle 2 | Nazeer | Data Input | 18-Mar-21 | 18-Mar-21 | 18-Mar-21 | 18-Mar-21
 |  |  |  |  |  | Batch | 19-Mar-21 | 19-Mar-21 | 19-Mar-21 | 19-Mar-21
 |  |  |  |  |  | Verification | 21-Mar-21 | 21-Mar-21 | 19-Mar-21 | 19-Mar-21
 |  |  |  |  |  | Re-run | 22-Mar-21 | 22-Mar-21 | 22-Mar-21 | 22-Mar-21

## Slide 16: Projection for next 2 weeks..contd
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
LAOS | AP | Automation | Regression | Cycle 2 | Bhanu | Data Input | 23-Mar-21 | 23-Mar-21 | 18-Mar-21 | 22-Mar-21
 |  |  |  |  |  | Batch | 24-Mar-21 | 24-Mar-21 | 23-Mar-21 | 23-Mar-21
 |  |  |  |  |  | Verification | 25-Mar-21 | 25-Mar-21 | 24-Mar-21 | 25-Mar-21
 |  |  |  |  |  | Re-run | 26-Mar-21 | 26-Mar-21 | 26-Mar-21 | 26-Mar-21
TWN | AP | Automation | Regression | Cycle 2 | Kritika,Bhanu&Nazeer | Data Input | 29-Mar-21 | 29-Mar-21 | 29-Mar-21 | 29-Mar-21
 |  |  |  |  |  | Batch | 30-Mar-21 | 30-Mar-21 | 30-Mar-21 | 30-Mar-21
 |  |  |  |  |  | Verification | 31-Mar-21 | 31-Mar-21 | 31-Mar-21 | 31-Mar-21
 |  |  |  |  |  | Re-run | 01-Apr-21 | 01-Apr-21 | 01-Apr-21 | 03-Apr-21
CHN | AP | Automation | Regression | Cycle 2 | Swati,Bhanu & Aishwarya | Data Input | 02-Apr-21 | 02-Apr-21 | 24-Mar-21 | 08-Apr-21
 |  |  |  |  |  | Batch | 05-Apr-21 | 05-Apr-21 | 08-Apr-21 | 08-Apr-21
 |  |  |  |  |  | Verification | 06-Apr-21 | 06-Apr-21 | 09-Apr-21 | 09-Apr-21
 |  |  |  |  |  | Re-run | 07-Apr-21 | 07-Apr-21 | 09-Apr-21 | 
AUS | AP | Manual | Regression | Cycle2 | Bhanu,Swati & Aishwarya | Execution | 08-Apr-21 | 10-Apr-21 | 22-Mar-21 | 12-Apr-21

## Slide 17: On – Going Tracking
Initiative Name | Current Status | Confluence link
Implementation of good practices. Draft V1. | Document available in confluence page | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK
Module for maintaining login credentials | Working as expected | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK