## Slide 1: PeopleSoft Automation
Participants : Sameer Khanna, Kathy Kha, Sidhant Dayal, Vineet Wadwekar, Shivangi Tyagi, Venkat P, Karthik R, Sourav Mitra, Shyam Jha, Ramesh N, Bhanu M and Jatin P.

## Slide 2
PeopleSoft HCM

## Slide 3
Summary – Regression Suite
Total Regression Test Cases
. Automated : 330
. Manual : 175
Progression Automation for
Corp X PI XI Sprint 4
. Total Tests : 114
. Manual Test: 53
. Reused existing automated tests : 56
. Automated/Automatable : 5/5
Team Commentary
Achievements from the past fortnight
ST for Sprint 4 stands at approx. 80% completion.
Comment on Summary – Regression Suite section
. Regression Testing for the last Sprint has been executed, 150 Regression test scripts have been successfully run.
. Full Regression suite will be executed on USYS2 once the data base is available after refresh.
Actions & Support
Support Needed
No open incidents or requests
Actions from previous meeting
N/A
Executive Summary for Core HR
Current area of focus:
System testing is currently underway. We have used existing PTF scripts to create test data for current sprint, as the testing in current Sprint involved Mail Notification verification, Report verification and IB messages verification.
Current status of the focus area: Green/Amber/Red
GREEN
Team
Jatin (Presenter)
John
From Core HR
Date: 14 Apr 2021

## Slide 4
PeopleSoft Core Finance- GL | AM |LA

## Slide 5
Summary – Regression Suite
Total Regression Test Cases
. Automated : 751
. Manual: 72
Progression Automation for
Corp X PI XI Sprint 3
. Total Tests : 15
. Reused existing automated tests : 0
. Automated/Automatable : 3/3
- Manual : 12
Team Commentary
Achievements from the past fortnight
Cycle 3 ST completed for China, Global ST is in progress and is on track
Comment on Summary – Regression Suite section
. Regression-Automation will completed by EOW. Manually testing for GL & AM is progress.
Comment on the Test Execution Plan vs Actual variance
. Initial variance due to delay in environment readiness but as picked up pace gradually
Comment on the defect distribution numbers
. Defects related with script/data as minimized. Encountered few environment issues
.
Actions & Support
Support Needed
INC3268563,INC3666177
Actions from previous meeting
China Online Journal Edit performance
Executive Summary for GL, AM & LA
Current area of focus: PeopleTools upgrade + GL selective adoption initiative.
System testing cycle 3 is currently underway. Cycle 1 has been completed on a lower version of tools and now closed. Cycle 2 testing was carried out in upgraded version and stands at 100% completion. Cycle 3 testing is in progress and expected to complete by 21st May.
Current status of the focus area: Green/Amber/Red
GREEN
Chart: 
| GL-CN | AM-CN | LA-CN | GL-AU
Script/Data | 4 | 4 | 0
Functional Defect | 6 | 2 | 2
Environment | 5 | 4 | 0
Chart: 
| 44296 | 44301 | 44306 | 44314 | 44323 | 44330 | 44337 | 44344
Planned Test Execution | 0 | 100 | 250 | 400 | 550 | 700 | 820
Actual Test Execution | 0 | 40 | 200 | 350 | 500 | 650
Column1
Column2
Column3
Column4
Team
Navneet (Presenter)
Ramesh
Santosh
Vishnu
Kiran
Harika
From Evolve & Protect
Date: 29 April 2021

## Slide 6
Chart: 
| 44127 | 44141 | 44155 | 44169 | 44183 | 44196
Planned Test Execution | 0 | 209 | 579 | 776
Actual Test Execution | 0 | 147 | 295 | 499 | 761 | 770
Column1
Column2
Column3
Column4
Chart: 
| GL-AU | GL-NZ | GL-UK | GL-SG | GL-HK | GL-FJ | GL-CH | AM-NZ | AM-UK | AM-CH
Script/Data | 30 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 11 | 5
Functional Defect | 17 | 2 | 2 | 3 | 2 | 1 | 5 | 2 | 1 | 1
Environments | 5 | 0 | 0 | 0 | 0 | 5 | 1 | 1 | 1 | 1

## Slide 7
Chart: 
| 44232 | 44246 | 44260 | 44274 | 44288 | 44302 | 44316
Planned Test Execution | 0 | 63 | 397 | 672 | 816 | 943
Actual Test Execution | 35 | 57 | 232 | 684 | 787 | 933
Column1
Column2
Column3
Column4
Chart: 
| GL-AU | GL-NZ | GL-UK | GL-SG | GL-HK | GL-FJ | GL-CH | AM-AU | AM-NZ | AM-CH
Script/Data | 8 | 16 | 17 | 13 | 16 | 1 | 18 | 1 | 0 | 12
Functional Defect | 5 | 2 | 1 | 0 | 1 | 0 | 7 | 0 | 0 | 7
Environments | 15 | 0 | 1 | 0 | 0 | 0 | 3 | 2 | 2 | 0

## Slide 8: Cycle 3 Execution Summary for PS GL/AM/LA
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 28h Apr | Pass | Fail | Not Executed | Defect Resolved | ETA
GL | 21st May | 393 | 42 | 435 | 415 | 415 | 0 | 20 | 3 out of 6 | 
AM | 14th-May | 238 | 30 | 268 | 260 | 260 | 0 | 8 | 2 out of 2 | 
LA | 21st-May | 108 | 0 | 108 | 108 | 108 | 0 | 0 | 2 out of 2 | 
Archival | 7th May | 12 | 0 | 12 | 9 | 9 | 0 | 3 | 3 out of 3 | 

## Slide 9: Projection for Next 2 weeks – GL/AM/LA

## Slide 10: Blocker & Environment issue – GL/AM/LA
Sl No | Backlog / Issue | Raised On | Owner | Status | Aging | Comment
1 | INC3268563 – Long running Online Journal Edit in China | 14th Dec 21 | Kiran | Testing completed | 83 | Build completed for EOD update changes, Unit test is in progress.
2 | INC3666177 - App Engine PSARCHIVE is running long in GBFAUQA1 | 21st Apr 21 | Yamini | Open | 20 | DB team working on it

## Slide 11
Source to Pay (S2P)

## Slide 12
Summary – Regression Suite
Total Regression Test Cases
. Automated (AP/Purchasing/E-Proc) : 456 & 95 & 44(Total of 568)
. Manual(AP/Purchasing): 106 & 4(Total of 110)
Progression Automation for
Corp X PI XI Sprint 4
. Total Tests : 24
Manual Tests : 11
. Reused existing automated tests : 2
. Automated/Automatable : 13/13
Team Commentary
Achievements from the past fortnight
. Completed Cycle-3 for E-Procurement Module with no issues. AP execution is currently in Progress. Done with reports and voucher related scripts. Yet to trigger few End-to-End Scenarios.
Comment on Summary – Regression Suite section
. Manual test Cases execution will be started by Monday next week and we are planning to complete the regression run by End of next week,i.e.21/05/2021.
Comment on the Test Execution Plan vs Actual variance
. Due to SIT test Execution , China UAT Support and Considering the S2P 22 May release priorities, Cycle-3 delayed a little. Hopefully, we will close it by next week.
Comment on the defect distribution numbers
.In Cycle-2,PR/Voucher approval users list page issue is fixed now and retest Succeded.
Actions & Support
Support Needed
.HCM-FMS integration testing is in final stage where the person basic sync is facing some SQL error which is currently being handled inside the squad with the help of Naveen.
Executive Summary for Bhanu
Current area of focus: People Tools upgrade + GL selective adoption initiative.
System testing cycle 3 is currently underway. Cycle 1 has been completed on a lower version of tools and now closed. Cycle 2 testing has been Completed in Upgraded version of tools and now closed. Cycle 3 testing is Currently in progress and is planned to complete on 14th May 2021.
Current status of the focus area: Green/Amber/Red
Greeen
Chart: 
| India | Australia
Script/Data | 0 | 0
Functional Defect | 0 | 0
Environment | 0 | 0
Intermittent Issue | 0 | 0
Chart: 
| 44309 | 44314 | 44320 | 44326 | 44333 | 44337
Planned Test Execution | 0 | 44 | 77 | 150 | 150 | 168
Actual Test Execution | 0 | 44 | 44 | 70
Column1
Column2
Column3
Column4
Team
Bhanu (Presenter)
Aishwarya
Swati
Nazeer
Kritika
From S2P Squad
Date: 12 May 2021

## Slide 13
Chart: 
| 44492 | 44506 | 44520 | 44534 | 44548 | 44554 | 44561
Planned Test Execution | 0 | 80 | 160 | 241 | 407 | 442
Actual Test Execution | 0 | 59 | 162 | 235 | 396 | 421 | 442
Column1
Column2
Column3
Column4
Chart: 
| AP | PUR | E-PROC
Functional/Scripts | 1 | 0 | 0
Environment | 0 | 0 | 0
Intermittent | 0 | 0 | 0
Build issue | 1 | 0 | 0

## Slide 14
Chart: 
| 44232 | 44246 | 44260 | 44274 | 44288 | 44302 | 44316
Planned Test Execution | 0 | 80 | 160 | 241 | 346 | 442
Actual Test Execution | 0 | 43 | 137 | 237 | 307 | 427 | 442
Column1
Column2
Column3
Column4
Chart: 
| Thailand | UK | Taiwan | China
Script/Data | 0 | 0 | 9 | 0
Functional Defect | 1 | 1 | 0 | 1
Environment | 0 | 0 | 0 | 0
Intermittent Issue | 0 | 0 | 0 | 0

## Slide 15: Cycle 3 Execution Summary for S2P
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 12th May | Pass | Fail | Not Executed | Defect Resolved | ETA
Purchasing-Cycle3 | 7 May 2021 | 65 | 4 | 69 | 0 | 0 | 0 | 69 | 0 | ETA:21st May 2021
E-Proc-Cycle3 | 28 Apr 2021 | 44 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | Completed
AP-Cycle3 | 14 May 2021 | 41 | 14 | 55 | 26 | 26 | 0 | 29 | 0 | ETA: 17th May 2021

## Slide 16: Execution Tracker for S2P Cycle-3:
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Test Cases
IND | E-PROC | Automation | Regression | Cycle 3 | Bhanu | Data Input | 23-Apr-21 | 23-Apr-21 | 26-Apr-21 | 27-Apr-21 | 44
 |  |  |  |  |  | Batch | 26-Apr-21 | 26-Apr-21 | 28-Apr-21 | 28-Apr-21 | 
 |  |  |  |  |  | Verification | 27-Apr-21 | 27-Apr-21 | 29-Apr-21 | 29-Apr-21 | 
 |  |  |  |  |  | Re-run | 28-Apr-21 | 28-Apr-21 |  |  | 
AUS | AP | Automation | Regression | Cycle 3 | Aishwarya&Bhanu | Data Input | 29-Apr-21 | 29-Apr-21 | 07-May-21 | 11-May-21 | 41
 |  |  |  |  |  | Batch | 30-Apr-21 | 30-Apr-21 | 12-May-21 |  | 
 |  |  |  |  |  | Verification | 03-May-21 | 03-May-21 |  |  | 
 |  |  |  |  |  | Re-run | 04-May-21 | 04-May-21 |  |  | 
IND | PUR | Automation | Regression | Cycle 3 | Nazeer | Data Input | 05-Apr-21 | 05-May-21 |  |  | 65
 |  |  |  |  |  | Batch | 06-May-21 | 06-May-21 |  |  | 
 |  |  |  |  |  | Verification | 07-May-21 | 07-May-21 |  |  | 
 |  |  |  |  |  | Re-run | 10-May-21 | 10-May-21 |  |  | 
AUS,IND | AP,E-Proc | Manual | Regression | Cycle3 | Bhanu , Swati & Aishwarya | Execution | 11-May-21 | 14-May-21 |  |  | 18

## Slide 17: Projection for next 2 weeks…
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Test Cases
AUS | AP | Automation | Regression | Cycle 3 | Bhanu | Batch | 17-Apr-21 | 17-Apr-21 |  |  | 29
 |  |  |  |  |  | Verification | 18-May-21 | 18-May-21 |  |  | 
 |  |  |  |  |  | Re-run | 19-May-21 | 19-May-21 |  |  | 
IND | PUR | Automation | Regression | Cycle 3 | Swati | Data Input | 17-Apr-21 | 17-May-21 |  |  | 65
 |  |  |  |  |  | Batch | 18-May-21 | 18-May-21 |  |  | 
 |  |  |  |  |  | Verification | 19-May-21 | 19-May-21 |  |  | 
 |  |  |  |  |  | Re-run | 20-May-21 | 20-May-21 |  |  | 
AUS,IND | AP,E-Proc | Manual | Regression | Cycle3 | Bhanu & Swati | Execution | 17-May-21 | 21-May-21 |  |  | 18

## Slide 18: Blocker & Environment issue – AP/E-Procurement/Purchasing
Sl No | Backlog / Issue | Raised On | Owner | Status | Aging | Comment
1 | Oracle SR (SR 3-25722848061) - Invalid view issue on Approver name hyper link on Payment Request Center page. | 20th Apr 21 | Nagaraju R | Closed | 6 | 
2 | REQ1763891-GBFUSUP2_PIA_ACCESS_REQUEST for missing roles | 27th Apr 21 | Chaitanya V | Closed | 2 | 
3 | REQ1750653-Request for DB access in CNFAUQA1 region | 21st Apr 21 | Lavanya C | Closed | 1 | 
4 | REQ1744961- Request to get the IB Connectivity between HCMUSYS1 and GBFAUQA1 to support SIT testing | 19th Apr 21 | Chaitanya V | Closed | 2 | 
5 | REQ1804850-Unable to access GBFAUQA1 DB | 12May 2021 | Chaitanya V | Closed | 1 | 

## Slide 19: On – Going Tracking
Initiative Name | Current Status | Confluence link
Implementation of good practices. Draft V1. | Document available in confluence page | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK
Module for maintaining login credentials | Working as expected | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK