## Slide 1: PeopleSoft Automation
Participants : Sameer Khanna, Kathy Kha, Sidhant Dayal, Vineet Wadwekar, Shivangi Tyagi, Venkat P, Karthik R, Sourav Mitra, Shyam Jha, Ramesh N, Bhanu M and Jatin P.

## Slide 2: Automation Status as on 17th Mar 2021
Focus Area | Regression Test Cases |  | Progression Automation – Identified in Innovation Sprint |  |  |  | Comment
 | Total Tests - Automated | Total Tests - Manual | Total Tests | Reusable automated Tests | Automatable | Automated | 
HCM | 315 | 175 | 19 | 4* | 0 | 0 | * Existing 4 automated test cases were reused.
GL | 428 | 34 | 10 | 0 | 9 | 9 | 1 Manual tests were created for DB verification related to table partitioning
AM | 250 | 18 | 7 | 0 | 7 | 3 | Pending tests to be automated by 22 Mar 21
LA | 94 | 0 | 4 | 0 | 4 | 2 | Pending tests to be automated by 22 Mar 21
AP | 419 | 29 | 3 | 0 | 1 | 1 | Automated the process “ANZ_PAP_EXT” until the extract generation.
Purchasing | 95 | 4 | 0 | 0 | 0 | 0 | 
E-Proc | 44 | 0 | 0 | 0 | 0 | 0 | 

## Slide 3: Execution Status as on 17th Mar 2021
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 17th Mar | Pass | Fail | Not Executed | Defect Resolved | ETA
GL - Cycle 1 | 25 Dec 2020 | 422 | 34 | 456 | 451 | 451 | 0 | 5 | 42 out of 42 | Completed except for 5 Manual Test cases related archival are deferred to Cycle 3 (ETA 11thh Apr) and 1 failed test case.
GL – Cycle 2 | 11 Apr 2021 | 422 | 34 | 456 | 271 | 252 | 19 | 185 | 36 out of 42 | ETA for pending Manual tests : 4 Apr(Sprint 1)
AM –Cycle 1 | 25 Dec 2020 | 238 | 18 | 256 | 256 | 256 | 0 | 0 | 3 out of 3 | Completed.
AM-Cycle 2 | 11 Apr 2021 | 238 | 18 | 256 | 238 | 238 | 0 | 18 | 11 out of 11 | ETA for pending Manual tests : 4 Apr(Sprint 1)

## Slide 4: Execution Status as on 17th March 2021
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 17th March | Pass | Fail | Not Executed | Defect Resolved | ETA
LA –Cycle 1 | 25 Dec 2020 | 78 | 0 | 78 | 78 | 78 | 0 | 0 | 0 | Completed.
LA- Cycle 2 | 11 Apr 2021 | 112 | 0 | 112 | 112 | 109 | 3 | 0 | 7 out of 7 | ETA for 3 failed Test: 17 Mar 2021
AP-Cycle1 |  | 419 | 26 | 445 | 445 | 445 | 0 | 0 | 1 out of 1 | Completed
AP-Cycle2 | 11 Apr 2021 | 423 | 26 | 449 | 243 | 232 | 11 | 180 | 0 | Test cases related to Report manager issue got re-tested and went well. Re-run expected to be finished this week for other failed cases.

## Slide 5: Execution Status as on 03rd Mar 2021
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 03 Mar 2021 | Pass | Fail | Not Executed | Defect Resolved | ETA
Purchasing-Cycle1 |  | 95 | 0 | 95 | 95 | 95 | 0 | 0 | 0 | Completed
Purchsing-Cycle2 | 5 Mar 2021 | 95 | 0 | 95 | 95 | 95 | 0 | 0 | 0 | Completed
E-Proc-Cycle1 |  | 44 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | Completed
E-Proc-Cycle2 | 11 Apr 2021 | 44 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | Completed(Note:Requisition approval workflow is considered for next PI as there are design-changes)

## Slide 6: Defect Distribution
Chart: GL Defect Distribution – Cycle 2
| AUS | NZL | GBR | FJI | CHN
Browser Issue | 15
Data Issue | 5 | 1 | 5 | 10
Long Running | 1 | 1 | 5
Development Issue | 3 | 1 | 1 | 2
PT upgrade- needs scripting | 2 | 1 | 1
Oracle Bug | 1
PTF Script Issue | 1 | 11 | 7
Environment Issue | 3

## Slide 7
Chart: AM Defect Distribution – Cycle 2
| AUS | NZL | CHN
Data Issue | 1 | 2 | 7
Environment Issue | 2
Development Issue | 7
User Access Issue | 5

## Slide 8: Bi weekly Execution Tracker – 17th Mar 2021
Country | Module | Category | Coverage | Test Cycle 2 | No of Iterations | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
AUS | AM | Automation | Regression | Cycle 2 | 3 | Data Input | 17-Feb-21 | 17-Feb-21 | 16-Feb-21 | 16-Feb-21
 |  |  |  |  |  | Batch | 17-Feb-21 | 18-Feb-21 | 16-Feb-21 | 17-Feb-21
 |  |  |  |  |  | Verification | 18-Feb-21 | 19-Feb-21 | 17-Feb-21 | 18-Feb-21
 |  |  |  |  |  | Re-run | 19-Feb-21 | 19-Feb-21 | 18-Feb-21 | 18-Feb-21
NZL | AM | Automation | Regression | Cycle 2 | 2 | Data Input | 22-Feb-21 | 22-Feb-21 | 18-Feb-21 | 19-Feb-21
 |  |  |  |  |  | Batch | 22-Feb-21 | 23-Feb-21 | 19-Feb-21 | 19-Feb-21
 |  |  |  |  |  | Verification | 23-Feb-21 | 24-Feb-21 | 22-Feb-21 | 22-Feb-21
 |  |  |  |  |  | Re-run | 24-Feb-21 | 24-Feb-21 | 22-Feb-21 | 22-Feb-21
GBR | AM | Automation | Regression | Cycle 2 | 1 | Data Input | 25-Feb-21 | 25-Feb-21 | 23-Feb-21 | 23-Feb-21
 |  |  |  |  |  | Batch | 25-Feb-21 | 26-Feb-21 | 23-Feb-21 | 23-Feb-21
 |  |  |  |  |  | Verification | 26-Feb-21 | 1-Mar-21 | 23-Feb-21 | 23-Feb-21
 |  |  |  |  |  | Re-run | 1-Mar-21 | 1-Mar-21 | 23-Feb-21 | 23-Feb-21

## Slide 9: Execution Tracker – contd … - 17th Mar 2021
Country | Module | Category | Coverage | Test Cycle 2 | No of Iterations | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
FJI | AM | Automation | Regression | Cycle 2 | 1 | Data Input | 2-Mar-21 | 2-Mar-21 | 24-Feb-21 | 24-Feb-21
 |  |  |  |  |  | Batch | 2-Mar-21 | 3-Mar-21 | 24-Feb-21 | 24-Feb-21
 |  |  |  |  |  | Verification | 3-Mar-21 | 4-Mar-21 | 25-Feb-21 | 25-Feb-21
 |  |  |  |  |  | Re-run | 4-Mar-21 | 4-Mar-21 | - | -
AUS | GL | Automation | Regression | Cycle 2 | 3 | Data Input | 18-Feb-21 | 19-Feb-21 | 17-Feb-21 | 18-Feb-21
 |  |  |  |  |  | Batch | 22-Feb-21 | 22-Feb-21 | 19-Feb-21 | 20-Feb-21
 |  |  |  |  |  | Verification | 22-Feb-21 | 23-Feb-21 | 22-Feb-21 | 22-feb-21
 |  |  |  |  |  | Re-run | 24-Feb-21 | 24-Feb-21 | - | -
NZL | GL | Automation | Regression | Cycle 2 | 2 | Data Input | 25-Feb-21 | 26-Feb-21 | 23-Feb-21 | 23-Feb-21
 |  |  |  |  |  | Batch | 26-Feb-21 | 1-Mar-21 | 24-Feb-21 | 24-Feb-21
 |  |  |  |  |  | Verification | 2-Mar-21 | 2-Mar-21 | 24-Feb-21 | 24-Feb-21
 |  |  |  |  |  | Re-run | 3-Mar-21 | 3-Mar-21 | 24-Feb-21 | 24-Feb-21

## Slide 10: Execution Tracker – contd …
Country | Module | Category | Coverage | Test Cycle 2 | No of Iterations | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
FJI | GL | Automation | Regression | Cycle 2 | 1 | Data Input | 3-Mar-21 | 3-Mar-21 | 25-Feb-21 | 25-Feb-21
 |  |  |  |  |  | Batch | 4-Mar-21 | 4-Mar-21 | 25-Feb-21 | 25-Feb-21
 |  |  |  |  |  | Verification | 4-Mar-21 | 4-Mar-21 | 25-Feb-21 | 25-Feb-21
LAOS | LA | Automation | Regression | Cycle 2 | 1 | Data Input | 15-Feb-21 | 15-Feb-21 | 15-Feb-21 | 15-Feb-21
 |  |  |  |  |  | Batch | 16-Feb-21 | 16-Feb-21 | 16-Feb-21 | 16-Feb-21
 |  |  |  |  |  | Verification | 17-Feb-21 | 18-Feb-21 | 17-Feb-21 | 18-Feb-21
 |  |  |  |  |  | Re-run | 19-Feb-21 | 22-Feb-21 | 19-Feb-21 | 22-Feb-21
HKG | LA | Automation | Regression | Cycle 2 | 1 | Data Input | 22-Feb-21 | 22-Feb-21 | 22-Feb-21 | 22-Feb-21
 |  |  |  |  |  | Batch | 23-Feb-21 | 24-Feb-21 | 23-Feb-21 | 24-Feb-21
 |  |  |  |  |  | Verification | 24-Feb-21 | 25-Feb-21 | 24-Feb-21 | 25-Feb-21
 |  |  |  |  |  | Re-run | 26-Feb-21 | 26-Feb-21 | 26-Feb-21 | 26-Feb-21

## Slide 11: Bi weekly Execution Tracker – 17th Mar 2021
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
SGP | AM | Automation | Regression | Cycle 2 | Ramesh | Data Input | 5-Mar-21 | 5-Mar-21 | 26-Feb-21 | 26-Feb-21
 |  |  |  |  |  | Batch | 8-Mar-21 | 8-Mar-21 | 26-Feb-21 | 26-Feb-21
 |  |  |  |  |  | Verification | 9-Mar-21 | 9-Mar-21 | 26-Feb-21 | 01-Mar-21
 |  |  |  |  |  | Re-run | 9-Mar-21 | 9-Mar-21 | - | -
HKG | AM | Automation | Regression | Cycle 2 | Ramesh | Data Input | 10-Mar-21 | 10-Mar-21 | 01-Mar-21 | 01-Mar-21
 |  |  |  |  |  | Batch | 10-Mar-21 | 11-Mar-21 | 02-Mar-21 | 02-Mar-21
 |  |  |  |  |  | Verification | 12-Mar-21 | 12-Mar-21 | 02-Mar-21 | 02-Mar-21
 |  |  |  |  |  | Re-run | 12-Mar-21 | 12-Mar-21 | - | -
CHN | AM | Automation | Regression | Cycle 2 | Ramesh | Data Input | 15-Mar-21 | 15-Mar-21 | 03-Mar-21 | 03-Mar-21
 |  |  |  |  |  | Batch | 15-Mar-21 | 16-Mar-21 | 03-Mar-21 | 04-Mar-21
 |  |  |  |  |  | Verification | 17-Mar-21 | 18-Mar-21 | 09-Mar-21 | 11-Mar-21
 |  |  |  |  |  | Re-run | 19-Mar-21 | 19-Mar-21 | 12-Mar-21 | 13-Mar-21

## Slide 12: Execution Tracker contd.. 17th March 2021
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
GBR | GL | Automation | Regression | Cycle 2 | Vishnu | Data Input | 5-Mar-21 | 5-Mar-21 | 27-Feb-21 | 27-Feb-21
 |  |  |  |  |  | Batch | 6-Mar-21 | 6-Mar-21 | 27-Feb-21 | 27-Feb-21
 |  |  |  |  |  | Verification | 7-Mar-21 | 8-Mar-21 | 01-Mar-21 | 03-Mar-21
 |  |  |  |  |  | Re-run | 8-Mar-21 | 8-Mar-21 | 03-Mar-21 | 03-Mar-21
SGP | GL | Automation | Regression | Cycle 2 | Vishnu | Data Input | 9-Mar-21 | 9-Mar-21 |  | 
 |  |  |  |  |  | Batch | 10-Mar-21 | 10-Mar-21 |  | 
 |  |  |  |  |  | Verification | 11-Mar-21 | 12-Mar-21 |  | 
 |  |  |  |  |  | Re-run | 12-Mar-21 | 12-Mar-21 |  | 
HKG | GL | Automation | Regression | Cycle 2 | Vishnu | Data Input | 15-Mar-21 | 15-Mar-21 |  | 
 |  |  |  |  |  | Batch | 16-Mar-21 | 16-Mar-21 |  | 
 |  |  |  |  |  | Verification | 17-Mar-21 | 17-Mar-21 |  | 
 |  |  |  |  |  | Re-Run | 17-Mar-21 | 17-Mar-21 |  | 

## Slide 13: Execution Tracker contd.. 17th March 2021
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
CHN | GL | Automation | Regression | Cycle 2 | Vishnu | Data input | 17-Mar-21 | 18-Mar-21 | 03-Mar-21 | 03-Mar-21
 |  |  |  |  |  | Batch | 18-Mar-21 | 19-Mar-21 | 03-Mar-21 | 04-Mar-21
 |  |  |  |  |  | Verification | 22-Mar-21 | 22-Mar-21 | 09-Mar-21 | 11-Mar-21
 |  |  |  |  |  | Re-run | 22-Mar-21 | 22-Mar-21 | 12-Mar-21 | 13-Mar-21
SGP | LA | Automation | Regression | Cycle 2 | Santosh | Data Input | 8-Mar-21 | 8-Mar-21 | 01-Mar-21 | 01-Mar-21
 |  |  |  |  |  | Batch | 8-Mar-21 | 9-Mar-21 | 02-Mar-21 | 02-Mar-21
 |  |  |  |  |  | Verification | 10-Mar-21 | 11-Mar-21 | 02-Mar-21 | 03-Mar-21
 |  |  |  |  |  | Re-run | 11-Mar-21 | 12-Mar-21 | 03-Mar-21 | 03-Mar-21
CHN | LA | Automation | Regression | Cycle 2 | Santosh | Data Input | 12-Mar-21 | 12-Mar-21 | 04-Mar-21 | 04-Mar-21
 |  |  |  |  |  | Batch | 15-Mar-21 | 16-Mar-21 | 04-Mar-21 | 05-Mar-21
 |  |  |  |  |  | Verification | 17-Mar-21 | 17-Mar-21 | 05-Mar-21 | 05-Mar-21
 |  |  |  |  |  | Re-run | 17-Mar-21 | 17-Mar-21 | 05-Mar-21 | 05-Mar-21

## Slide 14: Execution Tracker contd.. 17th March 2021
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
IND | Purchasing | Automation | Regression | Cycle 2 | Bhanu | Data Input | 8-Mar-21 | 8-Mar-21 | 8-Mar-21 | 8-Mar-21
 |  |  |  |  |  | Batch | 9-Mar-21 | 9-Mar-21 | 9-Mar-21 | 9-Mar-21
 |  |  |  |  |  | Verification | 10-Mar-21 | 10-Mar-21 | 10-Mar-21 | 10-Mar-21
 |  |  |  |  |  | Re-run | 11-Mar-21 | 11-Mar-21 | 11-Mar-21 | 11-Mar-21
IND | AP | Automation | Regression | Cycle 2 | Aishwarya | Data Input | 12-Mar-21 | 12-Mar-21 | 12-Mar-21 | 12-Mar-21
 |  |  |  |  |  | Batch | 15-Mar-21 | 15-Mar-21 | 15-Mar-21 | 15-Mar-21
 |  |  |  |  |  | Verification | 16-Mar-21 | 16-Mar-21 | 16-Mar-21 | 16-Mar-21
 |  |  |  |  |  | Re-run | 17-Mar-21 | 17-Mar-21 | 16-Mar-21 | 16-Mar-21
JPN | AP | Automation | Regression | Cycle 2 | Nazeer | Data Input | 18-Mar-21 | 18-Mar-21 | 18-Mar-21 | 
 |  |  |  |  |  | Batch | 19-Mar-21 | 19-Mar-21 |  | 
 |  |  |  |  |  | Verification | 21-Mar-21 | 21-Mar-21 |  | 
 |  |  |  |  |  | Re-run | 22-Mar-21 | 22-Mar-21 |  | 

## Slide 15: Execution Tracker contd.. 17th March 2021
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
AUS | AM | Automation | Progression | Cycle 2 | Navneet | Scripting | 15-Feb-21 | 10-Mar-21 | 15-Feb-21 | 
NZL | AM | Automation | Progression | Cycle 2 | Navneet | Scripting | 11-Mar-21 | 12-Mar-21 |  | ETA:24-Mar-21
CHN | AM | Automation | Progression | Cycle 2 | Navneet | Scripting | 15-Mar-21 | 17-Mar-21 |  | ETA:25-Mar-21
GBR | LA | Automation | Progression | Cycle 2 | Santosh | Scripting | 18-Mar-21 | 19-Mar-21 |  | ETA:31-Mar-21
LAO | LA | Automation | Progression | Cycle 2 | Santosh | Scripting | 19-Feb-21 | 12-Mar-21 | 19-Feb-21 | 18-Mar-21
CHN | LA | Automation | Progression | Cycle 2 | Santosh | Scripting | 15-Mar-21 | 19-Mar-21 |  | ETA:25-Mar-21

## Slide 16: Projection for next 2 weeks
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
SGP | GL | Automation | Regression | Cycle 2 | Vishnu | Data Input | 9-Mar-21 | 9-Mar-21 |  | 
 |  |  |  |  |  | Batch | 10-Mar-21 | 10-Mar-21 |  | 
 |  |  |  |  |  | Verification | 11-Mar-21 | 12-Mar-21 |  | 
 |  |  |  |  |  | Re-run | 12-Mar-21 | 12-Mar-21 |  | ETA:22-Mar-21
HKG | GL | Automation | Regression | Cycle 2 | Vishnu | Data Input | 15-Mar-21 | 15-Mar-21 |  | 
 |  |  |  |  |  | Batch | 16-Mar-21 | 16-Mar-21 |  | 
 |  |  |  |  |  | Verification | 17-Mar-21 | 17-Mar-21 |  | 
 |  |  |  |  |  | Re-Run | 17-Mar-21 | 17-Mar-21 |  | ETA:25-Mar-21
NZL | AM | Automation | Progression | Cycle 2 | Navneet | Scripting | 11-Mar-21 | 12-Mar-21 |  | ETA:24-Mar-21
CHN | AM | Automation | Progression | Cycle 2 | Navneet | Scripting | 15-Mar-21 | 17-Mar-21 |  | ETA:29-Mar-21

## Slide 17: Projection for next 2 weeks .. contd
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
GBR | LA | Automation | Progression | Cycle 2 | Santosh | Scripting | 18-Mar-21 | 19-Mar-21 |  | ETA:31-Mar-21
CHN | LA | Automation | Progression | Cycle 2 | Santosh | Scripting | 15-Mar-21 | 19-Mar-21 |  | ETA:25-Mar-21
CHN | GL | Manual | Regression | Cycle 2 | Simadri | Execution | 18-Mar-21 | 25-Mar-21 |  | 
AUS | GL | Manual | Regression | Cycle 2 | Simadri | Execution | 26-Mar-21 | 02-Mar-21 |  | 
CHN | AM | Manual | Regression | Cycle 2 | Ramesh | Execution | 16-Mar-21 | 24-Mar-21 |  | 
AUS | AM | Manual | Regression | Cycle 2 | Ramesh | Execution | 25-Mar-21 | 02-Apr-21 |  | 
AUS | PP | Automation | Regression | Cycle 2 | Santosh | Execution | 31-Mar-21 | 02-Apr-21 |  | 
AUS | PP | Manual | Regression | Cycle 2 | Navneet | Execution | 30-Mar-21 | 02-Apr-21 |  | 

## Slide 18: Projection for next 2 weeks..contd
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
LAOS | AP | Automation | Regression | Cycle 2 | Bhanu | Data Input | 23-Mar-21 | 23-Mar-21 | 18-Mar-21 | 
 |  |  |  |  |  | Batch | 24-Mar-21 | 24-Mar-21 |  | 
 |  |  |  |  |  | Verification | 25-Mar-21 | 25-Mar-21 |  | 
 |  |  |  |  |  | Re-run | 26-Mar-21 | 26-Mar-21 |  | 
TWN | AP | Automation | Regression | Cycle 2 | Kritika | Data Input | 29-Mar-21 | 29-Mar-21 |  | 
 |  |  |  |  |  | Batch | 30-Mar-21 | 30-Mar-21 |  | 
 |  |  |  |  |  | Verification | 31-Mar-21 | 31-Mar-21 |  | 
 |  |  |  |  |  | Re-run | 01-Apr-21 | 01-Apr-21 |  | 
CHN | AP | Automation | Regression | Cycle 2 | Swati | Data Input | 02-Apr-21 | 02-Apr-21 |  | 
 |  |  |  |  |  | Batch | 05-Apr-21 | 05-Apr-21 |  | 
 |  |  |  |  |  | Verification | 06-Apr-21 | 06-Apr-21 |  | 
 |  |  |  |  |  | Re-run | 07-Apr-21 | 07-Apr-21 |  | 
AUS | AP | Manual | Regression | Cycle2 | Bhanu & Aishwarya | Execution | 08-Apr-21 | 10-Apr-21 |  | 

## Slide 19: Blocker & Environment issue - New
Sl No | Backlog / Issue | Raised On | Owner | Status | Aging | Comment
1 | INC3509864 -Balance Compare Load ANZ_BALC_LD is failing in PT 8.58 for files larger than 156 lines | 24-Feb-21 | Navneet | Open | 16 | Oracle SR # 3-25335007731. PT 8.58.05 patching in progress
2 | INC3268563 – Long running Online Journal Edit in China | 14th Dec 21 | Kiran | Open | 69 | Testing in progress
3 | INC3512809 - Process in Queued Status in CNFUSYS1 | 03rd Mar 21 | Santosh | Closed | 1 | 
4 | REQ1666553- Access & PTF Login details for CNFUSYS1 environment. | 16th Mar 21 | Swati | Closed | 1 | 

## Slide 20: Blocker & Environment issue - History
Sl No | Backlog / Issue | Raised On | Owner | Status | Aging | Comment
1 | RITM1830269 - Identify the tablespace for APLARGE_GBL and APLARGE_NZL | 26th Feb 21 | Bhanu | Closed | 5 | 
2 | RITM1834750 - GBFUDEV1_Regular entry page issue | 01st Mar 21 | Bhanu | Closed | 8 | 
3 | INC3512818-PFT batch run is giving error | 03rd Mar 21 | Jatin | Closed | 1 | 
4 | INC3492739 -HCMUSYS1 is down. | 25th Feb 21 | Jatin | Closed | 4 | 
5 | RITM1838317 - increase tablespace size to 15 gb in APLARGE_GBL and APLARGE_NZL | 02nd Mar 21 | Bhanu | Closed | 1 | 
6 | INC3512809-Process in Queued Status in CNFUSYS1 | 03rd Feb 21 | Santosh | Closed | 1 | 
7 | INC3511503 – PTF Outage | 02nd Feb 21 | Ramesh | Closed | 1 | 
8 | INC3511503 - Login failing in Non-Prod PSFMS Environments with TNS Error | 02nd Feb 21 | Navneet | Closed | 1 | 
9 | INC3492502 - nVision Report is in initiated status for long time in QA1 Environment | 25th Feb 21 | Vishnu | Closed | 5 | 
10 | INC3489596 - Server reboot in the middle of batch run | 24th Feb 21 | Ramesh | Closed | 5 | 

## Slide 21: Blocker & Environment issue- History
Sl No | Backlog / Issue | Raised On | Owner | Status | Aging | Comment
11 | INC3434981 – Jobs failing with Out of memory issue | 9th Feb 21 | Venkat | Closed | 12 | 
12 | INC3438545 - Wrapper Jobs are going to queued in CNFUSYS1 region | 10th Feb 21 | Venkat | Closed | 5 | INC3438545 - Wrapper Jobs are going to queued in CNFUSYS1 region
13 | INC3438537 - Cross Reciprocal Process is running to Errors | 10th Feb 21 | Venkat | Closed | 2 | INC3438537 - Cross Reciprocal Process is running to Errors
14 | Oracle SR -SR 3-24746654751 : Test parameters are not getting fetched into the PTF editor when we try to open a test case | 15th Dec 20 | Ramesh Nellimarla | Closed | 41 | Issue is not seen in PT858, can be closed.
15 | Defect Id – COFES-602 Page Getting Expired while trying to Create Journals - CNFUSYS1 | 30th Nov 20 | Sourav M | Closed | 15 | 
16 | RITM1720028 - Process failed with error "unable to extend segment by 128 in undo tablespace 'UNDOTBS1'" in SYS1(GBPOC858) | 18th Jan 21 | DB Team | Closed | 2 | 

## Slide 22: Blocker & Environment issue - History
Sl No | Backlog / Issue | Raised On | Owner | Status | Aging | Comment
17 | INC3406832 – Reporting jobs are running to Errors in GBFUSUP2 region | 01st Feb 21 | Arvindan Jambu | Closed |  | 
18 | INC3414988 – Missing nVisions in GBPOC858 | 02nd Feb 21 | Arvindan Jambu | Closed |  | 
19 | INC3415013 - JEDIT and FS_JGEN process running long in GBPOC858 | 02nd Feb 21 | Madhav Mannem | Closed |  | 
20 | RITM1706427 – Request for connection settings for PT8.58 PTF | 12th Jan 21 | Arvindan Jambu | Closed |  | 
21 | RITM1724350 - Not able to run PTF tests in 8.58 in RD: APPAU301MEL0772.globaltest.anz.com | 19th Jan 21 | Arvindan Jambu | Closed |  | 
22 | RITM1706657 - FM Extract failed in GBFAUQA1 | 12th Jan 21 | Arvindan Jambu | Closed |  | 
23 | INC3342386 – Error while logging in to PTF (GBFAUQA1) | 11th Jan 21 | Arvindan Jambu | Closed |  | 
24 | INC3345167 – Error while logging in to PTF (GBFAUQA1) | 12th Jan 21 | Arvindan Jambu | Closed |  | 
25 | COFES- 461 / Oracle SR -3-24599858141 : SSL Error while trying to get the test script | 28th Oct | Madhav M | Closed |  | 

## Slide 23: Regression Execution Status - Cycle - 2
Chart: Regression Execution Status - Cycle - 2
| GL – Cycle 2 | AM-Cycle 2 | LA- Cycle 2 | AP-Cycle2 | Purchsing-Cycle2 | E-Proc-Cycle2
Automated | 422 | 238 | 78 | 423 | 95 | 44
Manual | 34 | 18 | 0 | 26 | 0 | 0
Total Regression test cases | 456 | 256 | 78 | 449 | 95 | 44
Executed till 2nd Feb | 84 | 140 | 0 | 46 | 63 | 44
Pass | 79 | 120 | 0 | 46 | 61 | 44
Fail | 5 | 20 | 0 | 0 | 2 | 0
Not Executed | 372 | 116 | 78 | 403 | 32 | 0

## Slide 24: On – Going Tracking
Initiative Name | Current Status | Confluence link
Implementation of good practices. Draft V1. | Document available in confluence page | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK
Module for maintaining login credentials | Working as expected | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK

## Slide 25: Automation Status as on 03rd Mar 2021
Focus Area | Regression Test Cases |  | Progression Automation – Identified in Sprint 6 |  |  |  | Comment
 | Total Tests - Automated | Total Tests - Manual | Total Tests | Reusable automated Tests | Automatable | Automated | 
HCM | 315 | 175 | 42 | 12* | 3 | 0 | * Existing 12 automated test cases were reused.
GL | 424 | 34 | 9 | 0 | 4 | 4 | 5 Manual tests were created for stories related to SIT / file transfers and Excel to CI
AM | 238 | 18 | 22 | 0 | 19 | 12 | Pending tests to be automated by 12 Mar 21
LA | 78 | 0 | 23 | 0 | 20 | 16 | Pending tests to be automated by 12 Mar 21
AP | 419 | 29 | 9 | 4 | 5 | 5 | 5 test cases are automated related to sanction screening adhoc template & Netreveal report
Purchasing | 95 | 4 | 6 | 2 | 2 | 2 | PO email dispatch for India were automated
E-Proc | 44 | 0 | 6 | 0 | 6 | 2 | Requisition Approval workflow changes are yet to automated post build completion with new design changes. Agreed to move to next PI.

## Slide 26: Execution Status as on 03rd Mar 2021
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 03rd Mar | Pass | Fail | Not Executed | Defect Resolved | ETA
GL - Cycle 1 | 25 Dec 2020 | 422 | 34 | 456 | 451 | 451 | 0 | 5 | 42 out of 42 | Completed except for 5 Manual Test cases related archival are deferred to Cycle 3 (ETA 11thh Apr) and 1 failed test case.
GL – Cycle 2 | 11 Apr 2021 | 422 | 34 | 456 | 220 | 209 | 11 | 236 | 33 out of 39 | 
AM –Cycle 1 | 25 Dec 2020 | 238 | 18 | 256 | 256 | 256 | 0 | 0 | 3 out of 3 | Completed.
AM-Cycle 2 | 11 Apr 2021 | 238 | 18 | 256 | 256 | 238 | 18 | 0 | 9 out of 11 | 

## Slide 27: Execution Status as on 03rd Mar 2021
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 03rd March | Pass | Fail | Not Executed | Defect Resolved | ETA
LA –Cycle 1 | 25 Dec 2020 | 78 | 0 | 78 | 78 | 78 | 0 | 0 | 0 | Completed.
LA- Cycle 2 | 11 Apr 2021 | 112 | 0 | 112 | 82 | 65 | 17 | 30 | 7 out of 7 | 
AP-Cycle1 |  | 419 | 26 | 445 | 445 | 445 | 0 | 0 | 1 out of 1 | Completed
AP-Cycle2 | 11 Apr 2021 | 423 | 26 | 449 | 205 | 191 | 14 | 218 | 0 | Identified the issues for the failures and expecting to run with updated data.

## Slide 28: Execution Status as on 03rd Mar 2021
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 03 Mar 2021 | Pass | Fail | Not Executed | Defect Resolved | ETA
Purchasing-Cycle1 |  | 95 | 0 | 95 | 95 | 95 | 0 | 0 | 0 | Completed
Purchsing-Cycle2 | 5 Mar 2021 | 95 | 0 | 95 | 95 | 90 | 5 | 0 | 0 | 
E-Proc-Cycle1 |  | 44 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | Completed
E-Proc-Cycle2 | 11 Apr 2021 | 44 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | Completed(Note:Requisition approval workflow needs to considered for next run with updated design-changes)

## Slide 29: Bi weekly Execution Tracker – 03rd March
Country | Module | Category | Coverage | Test Cycle 2 | No of Iterations | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
AUS | AM | Automation | Regression | Cycle 2 | 3 | Data Input | 17-Feb-21 | 17-Feb-21 | 16-Feb-21 | 16-Feb-21
 |  |  |  |  |  | Batch | 17-Feb-21 | 18-Feb-21 | 16-Feb-21 | 17-Feb-21
 |  |  |  |  |  | Verification | 18-Feb-21 | 19-Feb-21 | 17-Feb-21 | 18-Feb-21
 |  |  |  |  |  | Re-run | 19-Feb-21 | 19-Feb-21 | 18-Feb-21 | 18-Feb-21
NZL | AM | Automation | Regression | Cycle 2 | 2 | Data Input | 22-Feb-21 | 22-Feb-21 | 18-Feb-21 | 19-Feb-21
 |  |  |  |  |  | Batch | 22-Feb-21 | 23-Feb-21 | 19-Feb-21 | 19-Feb-21
 |  |  |  |  |  | Verification | 23-Feb-21 | 24-Feb-21 | 22-Feb-21 | 22-Feb-21
 |  |  |  |  |  | Re-run | 24-Feb-21 | 24-Feb-21 | 22-Feb-21 | 22-Feb-21
GBR | AM | Automation | Regression | Cycle 2 | 1 | Data Input | 25-Feb-21 | 25-Feb-21 | 23-Feb-21 | 23-Feb-21
 |  |  |  |  |  | Batch | 25-Feb-21 | 26-Feb-21 | 23-Feb-21 | 23-Feb-21
 |  |  |  |  |  | Verification | 26-Feb-21 | 1-Mar-21 | 23-Feb-21 | 23-Feb-21
 |  |  |  |  |  | Re-run | 1-Mar-21 | 1-Mar-21 | 23-Feb-21 | 23-Feb-21

## Slide 30: Execution Tracker – contd … - 03rd March
Country | Module | Category | Coverage | Test Cycle 2 | No of Iterations | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
FJI | AM | Automation | Regression | Cycle 2 | 1 | Data Input | 2-Mar-21 | 2-Mar-21 | 24-Feb-21 | 24-Feb-21
 |  |  |  |  |  | Batch | 2-Mar-21 | 3-Mar-21 | 24-Feb-21 | 24-Feb-21
 |  |  |  |  |  | Verification | 3-Mar-21 | 4-Mar-21 | 25-Feb-21 | 25-Feb-21
 |  |  |  |  |  | Re-run | 4-Mar-21 | 4-Mar-21 | - | -
AUS | GL | Automation | Regression | Cycle 2 | 3 | Data Input | 18-Feb-21 | 19-Feb-21 | 17-Feb-21 | 18-Feb-21
 |  |  |  |  |  | Batch | 22-Feb-21 | 22-Feb-21 | 19-Feb-21 | 20-Feb-21
 |  |  |  |  |  | Verification | 22-Feb-21 | 23-Feb-21 | 22-Feb-21 | 22-feb-21
 |  |  |  |  |  | Re-run | 24-Feb-21 | 24-Feb-21 | - | -
NZL | GL | Automation | Regression | Cycle 2 | 2 | Data Input | 25-Feb-21 | 26-Feb-21 | 23-Feb-21 | 23-Feb-21
 |  |  |  |  |  | Batch | 26-Feb-21 | 1-Mar-21 | 24-Feb-21 | 24-Feb-21
 |  |  |  |  |  | Verification | 2-Mar-21 | 2-Mar-21 | 24-Feb-21 | 24-Feb-21
 |  |  |  |  |  | Re-run | 3-Mar-21 | 3-Mar-21 | 24-Feb-21 | 24-Feb-21

## Slide 31: Execution Tracker – contd … - 03rd March
Country | Module | Category | Coverage | Test Cycle 2 | No of Iterations | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
FJI | GL | Automation | Regression | Cycle 2 | 1 | Data Input | 3-Mar-21 | 3-Mar-21 | 25-Feb-21 | 25-Feb-21
 |  |  |  |  |  | Batch | 4-Mar-21 | 4-Mar-21 | 25-Feb-21 | 25-Feb-21
 |  |  |  |  |  | Verification | 4-Mar-21 | 4-Mar-21 | 25-Feb-21 | 25-Feb-21
LAOS | LA | Automation | Regression | Cycle 2 | 1 | Data Input | 15-Feb-21 | 15-Feb-21 | 15-Feb-21 | 15-Feb-21
 |  |  |  |  |  | Batch | 16-Feb-21 | 16-Feb-21 | 16-Feb-21 | 16-Feb-21
 |  |  |  |  |  | Verification | 17-Feb-21 | 18-Feb-21 | 17-Feb-21 | 18-Feb-21
 |  |  |  |  |  | Re-run | 19-Feb-21 | 22-Feb-21 | 19-Feb-21 | 22-Feb-21
HKG | LA | Automation | Regression | Cycle 2 | 1 | Data Input | 22-Feb-21 | 22-Feb-21 | 22-Feb-21 | 22-Feb-21
 |  |  |  |  |  | Batch | 23-Feb-21 | 24-Feb-21 | 23-Feb-21 | 24-Feb-21
 |  |  |  |  |  | Verification | 24-Feb-21 | 25-Feb-21 | 24-Feb-21 | 25-Feb-21
 |  |  |  |  |  | Re-run | 26-Feb-21 | 26-Feb-21 | 26-Feb-21 | 26-Feb-21