## Slide 1: PeopleSoft Automation
Participants : Sameer Khanna, Kathy Kha, Sidhant Dayal, Vineet Wadwekar, Shivangi Tyagi, Venkat P, Karthik R, Sourav Mitra, Shyam Jha, Ramesh N, Bhanu M and Jatin P.

## Slide 2: Automation Status as on 20th Jan 2021
Focus Area | Regression Test Cases – As on 20th Jan |  | Progression Automation – Identified in Sprint 1 |  | Comment
 | Total | Verified / Working | Automatable | Automated | 
HCM | 305 | 305 | 6 | 6 | Existing 4 test cases were used for progression testing.
GL | 422 | 422 | 4 | 4 | 
AM | 238 | 238 |  |  | 
LA | 78 | 78 |  |  | 
AP | 419 | 419 |  |  | 
Purchasing | 95 | 95 |  |  | 
E-Proc | 44 | 44 |  |  | 

## Slide 3: Execution Status as on 20th Jan 2021
Focus Area | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Automated | Manual | Total Regression test cases | Executed till 20th Jan | Pass | Fail | Not Executed | Defect Resolved | ETA
GL - Cycle 1 | 422 | 34 | 456 | 451 | 451 | 0 | 5 | 42 out of 42 | Completed except for 5 Manual Test cases related archival are deferred to PT upgrade (ETA 20th Feb) and 1 failed test case.
GL – Cycle 2 | 422 | 34 | 456 | 49 | 24 | 25 | 407 | 1 out of 1 | Cycle 2 re-purposed to include PT upgrade and test execution is re-initiated in GBPOC858
AM –Cycle 1 | 238 | 18 | 256 | 256 | 256 | 0 | 0 | 3 out of 3 | Completed.
AM-Cycle 2 | 238 | 18 | 256 | 35 | 20 | 15 | 221 | 0 | Cycle 2 re-purposed to include PT upgrade and test execution is re-initiated in GBPOC858

## Slide 4: Execution Status as on 20th Jan 2021
Focus Area | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Automated | Manual | Total Regression test cases | Executed till 20th Jan | Pass | Fail | Not Executed | Defect Resolved | ETA
LA –Cycle 1 | 78 | 0 | 78 | 78 | 78 | 0 | 0 | 0 | Completed.
LA- Cycle 2 | 78 | 0 | 78 | 0 | 0 | 0 | 78 | 0 | Cycle 2 re-purposed to include PT upgrade and test execution is re-initiated in GBPOC858
AP-Cycle1 | 419 | 26 | 445 | 445 | 445 | 0 | 0 | 1 out of 1 | Completed
AP-Cycle2 | 419 | 26 | 445 | 0 | 0 | 0 | 445 | 0 | Cycle 2 re-purposed to include PT upgrade and test execution.
Purchasing-Cycle1 | 95 | 0 | 95 | 95 | 95 | 0 | 0 | 0 | Completed
Purchsing-Cycle2 | 95 | 0 | 95 | 15 | 15 | 0 | 80 | 0 | Cycle 2 re-purposed to include PT upgrade and test execution
E-Proc-Cycle1 | 44 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | Completed
E-Proc-Cycle2 | 44 | 0 | 44 | 21 | 21 | 0 | 23 | 0 | ETA-25th Jan

## Slide 5: Execution Status graphical representation
Chart: Execution Status
| GL - Cycle 1 | GL – Cycle 2 | AM –Cycle 1 | AM-Cycle 2 | LA –Cycle 1 | LA- Cycle 2 | AP-Cycle1 | AP-Cycle2 | Purchasing-Cycle1 | Purchsing-Cycle2 | E-Proc-Cycle1 | E-Proc-Cycle2
Automated | 422 | 422 | 238 | 238 | 78 | 78 | 419 | 419 | 95 | 95 | 44 | 44
Manual | 34 | 34 | 18 | 18 | 0 | 0 | 26 | 26 | 0 | 0 | 0 | 0
Total Regression test cases | 456 | 456 | 256 | 256 | 78 | 78 | 445 | 445 | 95 | 95 | 44 | 44
Executed till 20th Jan | 451 | 49 | 256 | 35 | 78 | 0 | 445 | 0 | 95 | 15 | 44 | 21
Pass | 451 | 24 | 256 | 20 | 78 | 0 | 445 | 0 | 95 | 15 | 44 | 21
Fail | 0 | 25 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Not Executed | 5 | 407 | 0 | 221 | 0 | 78 | 0 | 445 | 0 | 80 | 0 | 23

## Slide 6: Blocker & Environment issue
Sl No | Backlog / Issue | Raised On | Owner | Status | Comment
1 | Oracle SR -SR 3-24746654751 : Test parameters are not getting fetched into the PTF editor when we try to open a test case | 15th Dec 20 | Ramesh Nellimarla | Open | 
2 | RITM1720028 - Process failed with error "unable to extend segment by 128 in undo tablespace 'UNDOTBS1'" in SYS1(GBPOC858) | 18th Jan 21 | DB Team | Open | 
3 | Defect Id – COFES-602 Page Getting Expired while trying to Create Journals - CNFUSYS1 | 30th Nov 20 | Sourav M | Closed | 
4 | INC3342386 – Error while logging in to PTF (GBFAUQA1) | 11th Jan 21 | Arvindan Jambu | Closed | 
5 | INC3345167 – Error while logging in to PTF (GBFAUQA1) | 12th Jan 21 | Arvindan Jambu | Closed | 
6 | Environment issue . Defect Id – COFES- 461 / Oracle SR -3-24599858141 : SSL Error while trying to get the test script | 28th Oct | Madhav M | Closed | 

## Slide 7: Blocker & Environment issue
Sl No | Backlog / Issue | Raised On | Owner | Status | Comment
7 | RITM1706427 – Request for connection settings for PT8.58 PTF | 12th Jan 21 | Arvindan Jambu | Closed | 
8 | RITM1724350 - Not able to run PTF tests in 8.58 in RD: APPAU301MEL0772.globaltest.anz.com | 19th Jan 21 | Arvindan Jambu | Closed | 
9 | RITM1706657 - FM Extract failed in GBFAUQA1 | 12th Jan 21 | Arvindan Jambu | Closed | 

## Slide 8: On – Going Tracking
Initiative Name | Current Status | Confluence link
Implementation of good practices. Draft V1. | Document available in confluence page | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK
Module for maintaining login credentials | Working as expected | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK

## Slide 9: Execution Status as on 23rd Dec 2020
Focus Area | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Automated | Manual | Total Regression test cases | Executed till 23th Dec | Pass | Fail | Not Executed | Defect Resolved | ETA
GL - Cycle 1 | 422 | 34 | 456 | 451 | 450 | 1 | 5 | 40 out of 42 | Completed except for 5 Manual Test cases related archival are deferred to PT upgrade (ETA 20th Feb) and 1 failed test case.
GL – Cycle 2 | 422 | 34 | 456 | 80 | 39 | 41 | 376 | 0 out of 1 | ETA : 25th Jan. Parameter’s are not matching and unexpected error in QA Environment.
AM –Cycle 1 | 238 | 18 | 256 | 256 | 256 | 0 | 0 | 3 out of 3 | Completed.
AM-Cycle 2 | 238 | 18 | 256 | 72 | 63 | 9 | 184 | 0 | ETA : 25th Jan. Parameter’s are not matching and unexpected error in QA Environment.

## Slide 10: Execution Status as on 23rd Dec 2020
Focus Area | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Automated | Manual | Total Regression test cases | Executed till 23th Dec | Pass | Fail | Not Executed | Defect Resolved | ETA
LA –Cycle 1 | 78 | 0 | 78 | 75 | 75 | 0 | 3 | 0 | Completed, except for 3 Test cases which are archival are deferred due to dependency on upgraded PeopleTools instance (ETA : 31st Jan)
LA- Cycle 2 | 78 | 0 | 78 | 0 | 0 | 0 | 78 | 0 | ETA – 25th Jan
AP | 419 | 26 | 445 | 445 | 427 | 18 | 0 | 1 out of 1 | ETA :24th Dec.
Purchasing | 95 | 0 | 95 | 95 | 95 | 0 | 0 | 0 | Completed.