## Slide 1: PeopleSoft Automation
Participants : Sameer Khanna, Kathy Kha, Sidhant Dayal, Vineet Wadwekar, Shivangi Tyagi, Venkat P, Karthik R, Sourav Mitra, Shyam Jha, Ramesh N, Bhanu M and Jatin P.

## Slide 2
PeopleSoft HCM

## Slide 3
Summary – Regression Suite
Total Regression Test Cases
. Automated : 332
. Manual : 175
Progression Automation for
Corp X PI XI Sprint 5
. Total Tests : 130
. Manual Test: 63
. Reused existing automated tests : 65
. Automated/Automatable : 2/2
Team Commentary
Achievements from the past fortnight
ST for Sprint 5 stands at approx. 60% completion.
Comment on Summary – Regression Suite section
. Regression suite is planned and will be executed on 28th May.
Actions & Support
Support Needed
No open incidents or requests
Actions from previous meeting
N/A
Executive Summary for Core HR
Current area of focus:
System testing is currently underway. Existing PTF scripts were used to create test data for current sprint, as the testing in current Sprint involved Mail Notification verification, Report verification and changes in existing page functionality.
Current status of the focus area: Green/Amber/Red
GREEN
Team
Jatin (Presenter)
John
From Core HR
Date: 14 Apr 2021

## Slide 4
PeopleSoft Core Finance- GL | AM |LA

## Slide 5
Summary – Regression Suite
Total Regression Test Cases
. Automated : 751
. Manual: 72
Progression Automation for
Corp X PI XI Sprint 3
. Total Tests : 123
. Reused existing automated tests : 0
. Automated/Automatable : 84/84
- Manual : 39
Team Commentary
Achievements from the past fortnight
Cycle 3 ST completed for China and Global for GL,AM and LA
Comment on Summary – Regression Suite section
. Regression-Automation & Manual testing of GL,AM & LA completed.
Comment on the Test Execution Plan vs Actual variance
. There was a initial slack due to environment issues but was able to catchup later.
Comment on the defect distribution numbers
. Defects related with script/data reduced significantly in cycle -3.
.
Actions & Support
Support Needed
Actions from previous meeting
Executive Summary for GL, AM & LA
Current area of focus: People Tools upgrade + GL selective adoption initiative.
System testing - Cycle 3 was performed in upgraded environment GBFUSUP2 and CNFUSYS1 and was successfully completed last week.
Completed implementation of Login Library for all modules.
Work on PTF enhancements like batch optimization and dynamic parameterization is in progress.
Current status of the focus area: Green/Amber/Red
GREEN
Chart: 
| GL-CN | AM-CN | LA-CN | GL-AU
Script/Data | 4 | 4 | 0
Functional Defect | 6 | 2 | 2
Environment | 5 | 4 | 0
Chart: 
| 44296 | 44301 | 44306 | 44314 | 44323 | 44330 | 44337 | 44344
Planned Test Execution | 0 | 100 | 250 | 400 | 550 | 700 | 750
Actual Test Execution | 0 | 50 | 200 | 350 | 500 | 650 | 750
Column1
Column2
Column3
Column4
Team
Navneet
Ramesh (Presenter)
Santosh
Vishnu
Kiran
Harika
From Evolve & Protect
Date: 26 May 2021

## Slide 6
Chart: 
| 44127 | 44141 | 44155 | 44169 | 44183 | 44196
Planned Test Execution | 0 | 209 | 579 | 776
Actual Test Execution | 0 | 147 | 295 | 499 | 761 | 770
Column1
Column2
Column3
Column4
Chart: 
| GL-AU | GL-NZ | GL-UK | GL-SG | GL-HK | GL-FJ | GL-CH | AM-NZ | AM-UK | AM-CH
Script/Data | 30 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 11 | 5
Functional Defect | 17 | 2 | 2 | 3 | 2 | 1 | 5 | 2 | 1 | 1
Environments | 5 | 0 | 0 | 0 | 0 | 5 | 1 | 1 | 1 | 1

## Slide 7
Chart: 
| 44232 | 44246 | 44260 | 44274 | 44288 | 44302 | 44316
Planned Test Execution | 0 | 63 | 397 | 672 | 816 | 943
Actual Test Execution | 35 | 57 | 232 | 684 | 787 | 933
Column1
Column2
Column3
Column4
Chart: 
| GL-AU | GL-NZ | GL-UK | GL-SG | GL-HK | GL-FJ | GL-CH | AM-AU | AM-NZ | AM-CH
Script/Data | 8 | 16 | 17 | 13 | 16 | 1 | 18 | 1 | 0 | 12
Functional Defect | 5 | 2 | 1 | 0 | 1 | 0 | 7 | 0 | 0 | 7
Environments | 15 | 0 | 1 | 0 | 0 | 0 | 3 | 2 | 2 | 0

## Slide 8: Cycle 3 Execution Summary for PS GL/AM/LA
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 28h Apr | Pass | Fail | Not Executed | Defect Resolved | ETA
GL | 21st May | 393 | 42 | 435 | 435 | 435 | 0 | 0 | 6 out of 6 | 
AM | 14th-May | 238 | 30 | 268 | 268 | 268 | 0 | 0 | 2 out of 2 | 
LA | 21st-May | 108 | 0 | 108 | 108 | 108 | 0 | 0 | 2 out of 2 | 
Archival | 7th May | 12 | 0 | 12 | 12 | 12 | 0 | 0 | 3 out of 3 | 

## Slide 9: Projection for Next 2 weeks – GL/AM/LA

## Slide 10: Blocker & Environment issue – GL/AM/LA
Sl No | Backlog / Issue | Raised On | Owner | Status | Aging | Comment
1 | COFES-812- Data for all triggers missing in CNFUSYS1 and CNFUQA1 | 26th Apr 21 | Madhav | Open | 30 | DB team working on it
2 | INC3666177 - App Engine PSARCHIVE is running long in GBFAUQA1 | 21st Apr 21 | Yamini | Open | 35 | DB team working on it
3 | COFES-832 – Entries are generated with reverse Signage in CHINA QA region for Lease transaction | 18th May 21 | Venkat | Open | 8 | 

## Slide 11
Source to Pay (S2P)

## Slide 12
Summary – Regression Suite
Total Regression Test Cases
. Automated (AP/Purchasing/E-Proc) : 456 & 95 & 44(Total of 568)
. Manual(AP/Purchasing): 106 & 4(Total of 110)
Progression Automation for
Corp X PI XI Sprint 5
. Total Tests : 13
Manual Tests : 10
. Reused existing automated tests : 1
. Automated/Automatable : 2/2
Team Commentary
Achievements from the past fortnight
. Completed Cycle-3 for Accounts payable and Purchasing module successfully
Comment on Summary – Regression Suite section
. Even, in-Scope Manual test Cases execution is Completed.
Comment on the Test Execution Plan vs Actual variance
. Due to SIT test Execution & China UAT Support ,Cycle-3 got deviated a little from the plan. But, we managed to close it this week.
Comment on the defect distribution numbers
.In Cycle-3,Script issues causing defects are reduced.
Actions & Support
Support Needed
.Ariba remittance files issue is still open which Purnendu is currently looking in. We Will get it re-tested once we get a fix.No other pending incidents/requests.
Executive Summary for Bhanu
Current area of focus: People Tools upgrade + GL selective adoption initiative.
System testing cycle 3 is completed this week in Upgraded environment(GBFUSUP2). Cycle 1 has been completed on a lower version of tools and now closed. Cycle 2 testing has been Completed in Upgraded version of tools and now closed.
Current status of the focus area: Green/Amber/Red
Green
Chart: 
| India | Australia
Script/Data | 3 | 6
Functional Defect | 0 | 0
Environment | 0 | 0
Intermittent Issue | 0 | 0
Chart: 
| 44309 | 44314 | 44320 | 44326 | 44333 | 44337 | 44342
Planned Test Execution | 0 | 44 | 77 | 150 | 150 | 168
Actual Test Execution | 0 | 44 | 44 | 70 | 116 | 152 | 168
Column1
Column2
Column3
Column4
Team
Bhanu (Presenter)
Aishwarya
Swati
Nazeer
Kritika
From S2P Squad
Date: 26 May 2021

## Slide 13
Chart: 
| 44492 | 44506 | 44520 | 44534 | 44548 | 44554 | 44561
Planned Test Execution | 0 | 80 | 160 | 241 | 407 | 442
Actual Test Execution | 0 | 59 | 162 | 235 | 396 | 421 | 442
Column1
Column2
Column3
Column4
Chart: 
| AP | PUR | E-PROC
Functional/Scripts | 1 | 0 | 0
Environment | 0 | 0 | 0
Intermittent | 0 | 0 | 0
Build issue | 1 | 0 | 0

## Slide 14
Chart: 
| 44232 | 44246 | 44260 | 44274 | 44288 | 44302 | 44316
Planned Test Execution | 0 | 80 | 160 | 241 | 346 | 442
Actual Test Execution | 0 | 43 | 137 | 237 | 307 | 427 | 442
Column1
Column2
Column3
Column4
Chart: 
| Thailand | UK | Taiwan | China
Script/Data | 0 | 0 | 9 | 0
Functional Defect | 1 | 1 | 0 | 1
Environment | 0 | 0 | 0 | 0
Intermittent Issue | 0 | 0 | 0 | 0

## Slide 15: Cycle 3 Execution Summary for S2P
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 26th May | Pass | Fail | Not Executed | Defect Resolved | ETA
Purchasing-Cycle3 | 7 May 2021 | 65 | 4 | 69 | 69 | 69 | 0 | 0 | 3 of 3 | Completed
E-Proc-Cycle3 | 28 Apr 2021 | 44 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | Completed
AP-Cycle3 | 14 May 2021 | 41 | 14 | 55 | 55 | 55 | 0 | 0 | 6 of 6 | Completed

## Slide 16: Execution Tracker for S2P Cycle-3:
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Test Cases
AUS | AP | Automation | Regression | Cycle 3 | Bhanu | Batch | 17-May-21 | 17-May-21 | 17-May-21 | 17-May-21 | 29
 |  |  |  |  |  | Verification | 18-May-21 | 18-May-21 | 18-May-21 | 19-May-21 | 
 |  |  |  |  |  | Re-run | 19-May-21 | 19-May-21 | 20-May-21 | 21-May-21 | 
IND | PUR | Automation | Regression | Cycle 3 | Swati | Data Input | 17-Apr-21 | 17-May-21 | 18-May-21 | 19-May-21 | 65
 |  |  |  |  |  | Batch | 18-May-21 | 18-May-21 | 20-May-21 | 20-May-21 | 
 |  |  |  |  |  | Verification | 19-May-21 | 19-May-21 | 21-May-21 | 24-May-21 | 
 |  |  |  |  |  | Re-run | 20-May-21 | 20-May-21 | 25-May-21 | 26-May-21 | 
AUS,IND | AP,E-Proc | Manual | Regression | Cycle3 | Bhanu | Execution | 17-May-21 | 21-May-21 | 20-May-21 | 24-May-21 | 18

## Slide 17: Projection for next 2 weeks…
Activity | Login Library Implementation |  |  |  |  |  |  |  | 
Module & Status | AP | Current Status | ETA | PUR | Current Status | ETA | E-PROC | Current Status | ETA
Country | AUS | 40% | 7th Jun’21 | IND | 20% | 7 Jun’21 | IND | 20% | 7 Jun’21
 | CHN | 0% | 14 Jun’21 |  |  |  | NZL | 0% | 14 Jun’21
 | NZL | 0% | 14 Jun’21 |  |  |  |  |  | 
 | IND | 0% | 14 Jun’21 |  |  |  |  |  | 
 | SGP | 0% | 14 Jun’21 |  |  |  |  |  | 
 | TWN | 0% | 14 Jun’21 |  |  |  |  |  | 
 | JPN | 0% | 14 Jun’21 |  |  |  |  |  | 
 | LAOS | 0% | 14 Jun’21 |  |  |  |  |  | 
 | VNM | 0% | 14 Jun’21 |  |  |  |  |  | 

## Slide 18: Blocker & Environment issue – AP/E-Procurement/Purchasing
Sl No | Backlog / Issue | Raised On | Owner | Status | Aging | Comment
1 | PTPS-1055- Remittance files for Ariba are getting generated with no data in it. | 24th May 21 | Purnendu | Open | 3 | 

## Slide 19: On – Going Tracking
Initiative Name | Current Status | Confluence link
Implementation of good practices. Draft V1. | Document available in confluence page | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK
Module for maintaining login credentials | Working as expected | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK