## Slide 1: PeopleSoft Automation
Participants : Sameer Khanna, Kathy Kha, Sidhant Dayal, Vineet Wadwekar, Shivangi Tyagi, Venkat P, Karthik R, Sourav Mitra, Shyam Jha, Ramesh N, Bhanu M and Jatin P.

## Slide 2
PeopleSoft HCM

## Slide 3
Summary – Regression Suite
Total Regression Test Cases
. Automated : 317
. Manual : 175
Progression Automation for
Corp X PI XI Sprint 1
. Total Tests : 40
. Reused existing automated tests : - 7
. Automated/Automatable : 2/2
Team Commentary
Achievements from the past fortnight
ST for Sprint 1 stands at 60% completion.
Comment on Summary – Regression Suite section
.Regression Testing for the last Sprint has been completed, progression testing is in progress. We have planed to run the 40 regression test scripts for the current Sprint-1 on 01-04-2021, which includes the test scripts related to ADMIN and MSS.
Comment on the Test Execution Plan vs Actual variance
. N/A
Actions & Support
Support Needed
No open incidents or requests
Actions from previous meeting
N/A
Executive Summary for Core HR
Current area of focus:
System testing is currently underway. We used existing PTF scripts to create test data for current sprint, as most of the testing involved Mail Notification testing, Report testing including change in page functionality for already available PTF scripts.
Current status of the focus area: Green/Amber/Red
GREEN
Chart: 
| GL-AU | GL-NZ | GL-UK | GL-SG | GL-HK | GL-CH | GL-FJ | AM-AU | AM-NZ | AM-CH
Script/Data
Functional Defect
Environment
Chart: 
| 44272 | 44273 | 44274 | 44277 | 44278 | 44279 | 44280 | 44281 | 44284 | 44285 | 44286
Planned Test Execution
Actual Test Execution
Column1
Column2
Column3
Column4
Team
Jatin (Presenter)
John
From Core HR
Date: 31 March 2021

## Slide 4
PeopleSoft Core Finance- GL | AM |LA

## Slide 5
Summary – Regression Suite
Total Regression Test Cases
. Automated : 738
. Manual: 52
Progression Automation for
Corp X PI XI Sprint 1
. Total Tests : 41
. Reused existing automated tests : 0
. Automated/Automatable : 28/28
Team Commentary
Achievements from the past fortnight
ST completed for China, ST for Global stands at 80% completion
Comment on Summary – Regression Suite section
.13 tests were run manually which include Excel loaders and Config checks.
Comment on the Test Execution Plan vs Actual variance
. Minor variance due to time for defect resolution and retesting.
Comment on the defect distribution numbers
. There are only 3 outstanding defects
.
Actions & Support
Support Needed
No open incidents or requests
Actions from previous meeting
Balance Compare Load issue
China Online Journal Edit performance
Executive Summary for GL, AM & LA
Current area of focus: PeopleTools upgrade + GL selective adoption initiative.
System testing cycle 2 is currently underway. Cycle 1 has been completed on a lower version of tools and now closed. Cycle 2 testing is currently in progress is planned to complete on 12th April 2021.
Current status of the focus area: Green/Amber/Red
GREEN
Chart: 
| GL-AU | GL-NZ | GL-UK | GL-SG | GL-HK | GL-CH | GL-FJ | AM-AU | AM-NZ | AM-CH
Script/Data | 8 | 16 | 17 | 13 | 16 | 18 | 1 | 1 | 0 | 12
Functional Defect | 5 | 2 | 1 | 0 | 1 | 7 | 0 | 0 | 0 | 7
Environment | 15 | 0 | 1 | 0 | 0 | 3 | 0 | 2 | 2 | 0
Chart: 
| 44272 | 44273 | 44274 | 44277 | 44278 | 44279 | 44280 | 44281 | 44284 | 44285 | 44286
Planned Test Execution | 49 | 9 | 19 | 9 | 59 | 8 | 14 | 9 | 9 | 9 | 9
Actual Test Execution | 59 | 57 | 20 | 12 | 22 | 7 | 7 | 5 | 3 | 3 | 6
Column1
Column2
Column3
Column4
Team
Navneet (Presenter)
Ramesh
Santosh
Vishnu
Kiran
Harika
From Evolve & Protect
Date: 31 March 2021

## Slide 6: Cycle 2 Execution Summary for PS GL/AM/LA
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 31st Mar | Pass | Fail | Not Executed | Defect Resolved | ETA
GL | 11 Apr 2021 | 422 | 34 | 456 | 433 | 432 | 1 | 23 | 45 out of 46 | ETA for pending Manual tests : 4 Apr(Sprint 1)
AM | 11 Apr 2021 | 238 | 18 | 256 | 249 | 249 | 0 | 7 | 17 out of 17 | ETA for pending Manual tests : 4 Apr(Sprint 1)
LA | 11 Apr 2021 | 112 | 0 | 112 | 112 | 112 | 0 | 0 | 7 out of 7 | Completed

## Slide 7: Execution Tracker –GL/AM/LA
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
SGP | GL | Automation | Regression | Cycle 2 | Vishnu | Data Input | 9-Mar-21 | 9-Mar-21 | 9-Mar-21 | 10-Mar-21
 |  |  |  |  |  | Batch | 10-Mar-21 | 10-Mar-21 | 16-Mar-21 | 17-Mar-21
 |  |  |  |  |  | Verification | 11-Mar-21 | 12-Mar-21 | 17-Mar-21 | 17-Mar-21
 |  |  |  |  |  | Re-run | 12-Mar-21 | 12-Mar-21 | 19-Mar-21 | 22-Mar-21
HKG | GL | Automation | Regression | Cycle 2 | Vishnu | Data Input | 15-Mar-21 | 15-Mar-21 | 16-Mar-21 | 16-Mar-21
 |  |  |  |  |  | Batch | 16-Mar-21 | 16-Mar-21 | 18-Mar-21 | 18-Mar-21
 |  |  |  |  |  | Verification | 17-Mar-21 | 17-Mar-21 | 19-Mar-21 | 19-Mar-21
 |  |  |  |  |  | Re-Run | 17-Mar-21 | 17-Mar-21 | 22-Mar-21 | 23-Mar-21
NZL | AM | Automation | Progression | Cycle 2 | Navneet | Scripting | 11-Mar-21 | 12-Mar-21 | 17-Mar-21 | 18-Mar-21
CHN | AM | Automation | Progression | Cycle 2 | Navneet | Scripting | 15-Mar-21 | 17-Mar-21 | 19-Mar-21 | 24-Mar-21

## Slide 8: Execution Tracker.. contd
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
HKG | LA | Automation | Progression | Cycle 2 | Santosh | Scripting | 18-Mar-21 | 19-Mar-21 |  | ETA 8 Apr
CHN | LA | Automation | Progression | Cycle 2 | Santosh | Scripting | 15-Mar-21 | 19-Mar-21 | 19-Mar-21 | 24-Mar-21
CHN | GL | Manual | Regression | Cycle 2 | Simadri | Execution | 18-Mar-21 | 25-Mar-21 | 18-Mar-21 | 29-Mar-21
AUS | GL | Manual | Regression | Cycle 2 | Simadri | Execution | 26-Mar-21 | 02-Apr-21 | 30-Mar-21 | ETA: 6-Apr
CHN | AM | Manual | Regression | Cycle 2 | Ramesh | Execution | 16-Mar-21 | 24-Mar-21 | 16-Mar-21 | 29-Apr-21
AUS | AM | Manual | Regression | Cycle 2 | Ramesh | Execution | 25-Mar-21 | 02-Apr-21 | 30-Apr-21 | ETA: 6Apr
AUS | PP | Automation | Regression | Cycle 2 | Santosh | Execution | 31-Mar-21 | 02-Apr-21 |  | ETA 9 Apr
AUS | PP | Manual | Regression | Cycle 2 | Navneet | Execution | 30-Mar-21 | 02-Apr-21 |  | ETA 12 Apr

## Slide 9: Projection for Next 2 weeks – GL/AM/LA
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Test Cases
AUS | AM | Manual | Regression | Cycle 2 | Ramesh | Execution | 01-Apr-21 | 07-Apr-21 | 18
AUS | GL | Manual | Regression | Cycle 2 | Vishnu | Regression | 01-Apr-21 | 07-Apr-21 | 22
LAO | LA | Automation | Progression | Cycle 2 | Santosh | Execution | 01-Apr-21 | 5-Apr-21 | 22
HKG | LA | Automation | Progression | Cycle 2 | Santosh | Execution | 6-Apr-21 | 8-Apr-21 | 22
SGP | LA | Automation | Progression | Cycle 2 | Santosh | Execution | 9-Apr-21 | 12-Apr-21 | 22
AUS | AM | Manual | Progression | Cycle 2 | Navneet | Execution | 05-Apr-21 | 07-Apr-21 | 12
AUS | AM | Automation | Progression | Cycle 2 | Navneet | Execution | 08-Apr-21 | 08-Apr-21 | 7
AUS | PP | Automation | Regression | Cycle 2 | Ramesh | Execution | 08-Apr-21 | 09-Apr-21 | 10
AUS | PP | Manual | Regression | Cycle 2 | Navneet | Execution | 09-Mar-21 | 12-Apr-21 | 15
GBL | Archival | Batch | Regression | Cycle 2/3 | Simadri | Execution | 05-Apr-21 | 12-Apr-21 | 26

## Slide 10: Blocker & Environment issue – GL/AM/LA
Sl No | Backlog / Issue | Raised On | Owner | Status | Aging | Comment
1 | INC3509864 -Balance Compare Load ANZ_BALC_LD is failing in PT 8.58 for files larger than 156 lines | 24-Feb-21 | Navneet | Closed | 20 | 
2 | INC3268563 – Long running Online Journal Edit in China | 14th Dec 21 | Kiran | Open | 73 | Testing in progress

## Slide 11: Cycle 1 Execution Summary for PS GL
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 31st Mar | Pass | Fail | Not Executed | Defect Resolved | ETA
GL - Cycle 1 | 25 Dec 2020 | 422 | 34 | 456 | 451 | 451 | 0 | 5 | 42 out of 42 | Completed except for 5 Manual Test cases related archival are deferred to Cycle 3 (ETA 11thh Apr) and 1 failed test case.
AM –Cycle 1 | 25 Dec 2020 | 238 | 18 | 256 | 256 | 256 | 0 | 0 | 3 out of 3 | Completed.
LA –Cycle 1 | 25 Dec 2020 | 78 | 0 | 78 | 78 | 78 | 0 | 0 | 0 | Completed.

## Slide 12
Chart: 
| Day 1 - AU | Day 2 - AU | Day 3 - IN | Day 4 - IN | Day 5 - NZ | Day 6 - NZ
Planned Test Execution | 5 | 10 | 12 | 16 | 16 | 25
Actual Test Execution | 4 | 9 | 10 | 15 | 16 | 23
Column1
Column2
Column3
Column4
Chart: 
| Country 1 | Country 2 | Country 3 | Country 4
Reason 1 | 4 | 2 | 3 | 4
Reason 2 | 2 | 4 | 1 | 2
Reason 3 | 2 | 2 | 3 | 4

## Slide 13
Source to Pay (S2P)

## Slide 14
Summary – Regression Suite
Total Regression Test Cases
. Automated (AP/Purchasing/E-Proc) : 419 & 95 & 44(Total of 558)
. Manual(AP/Purchasing): 29 & 4(Total of 33)
Progression Automation for
Corp X PI XI Sprint 1
. Total Tests : 19
. Reused existing automated tests : -
. Automated/Automatable : 16/19
Team Commentary
Achievements from the past fortnight
. Completed AP test execution for LAOS, Japan; Manual scenarios execution got started(19-Passed;10-Failed;4-Yet to run)
Comment on Summary – Regression Suite section
. AP Taiwan batch execution verification is in Progress.
Comment on the Test Execution Plan vs Actual variance
. As per the Plan, we have completed AP module execution for Japan , Laos
Comment on the defect distribution numbers
. In China, Voucher Save wasn’t happening which is Closed now and retested Successfully.
PR/Voucher approval users list page issue is yet to be fixed
The execution details for cycle 1 (now closed) is available on the last slide.
Actions & Support
Support Needed
. CNFUSYS1 with latest refresh of PROD.
.Voucher/PR approver page issue. Currently, Naveen from our squad is looking into it.
Executive Summary for Bhanu
Current area of focus: People Tools upgrade + GL selective adoption initiative.
System testing cycle 2 is currently underway. Cycle 1 has been completed on a lower version of tools and now closed. Cycle 2 testing is currently in progress is planned to complete on 12th April 2021.
Current status of the focus area: Green
Chart: 
| Thailand | UK | Taiwan
Script/Data | 0 | 0 | 8
Functional Defect | 5 | 5 | 0
Environment | 0 | 0 | 0
Intermittent Issue | 0 | 0 | 13
Chart: 
| Day 2 - JPN | Day3 - JPN | Day 6 - LAOS | Day 7 - LAOS | Day 13 - TWN
Planned Test Execution | 20 | 21 | 19 | 21 | 42
Actual Test Execution | 20 | 21 | 18 | 22 | 42
Column1
Column2
Column3
Column4
Team
Bhanu Chandhar Nynari (Presenter)
From S2P Squad
Date: 31 March 2021

## Slide 15
Chart: 
| Day 1 - AP | Day 2 - AP | Day 3 - AP | Day 4 - AP | Day 5 - AP | Day 6 - AP | Day 7 - AP | Day 8 - AP | Day 3 - PUR | Day 4 - PUR | Day 5 - PUR | Day 6 -E-PRO
Planned Test Execution | 51 | 50 | 60 | 51 | 73 | 61 | 60 | 79 | 30 | 30 | 35 | 44
Actual Test Execution | 51 | 50 | 60 | 51 | 73 | 61 | 60 | 79 | 30 | 30 | 35 | 44
Column1
Column2
Column3
Column4
Chart: 
| AP | PUR | E-PROC
Functional/Scripts | 1 | 0 | 0
Environment | 0 | 0 | 0
Intermittent | 0 | 0 | 0

## Slide 16: Cycle 2 Execution Summary for S2P
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 17th Mar | Pass | Fail | Not Executed | Defect Resolved | ETA
Purchasing-Cycle2 | 5 Mar 2021 | 95 | 0 | 95 | 95 | 95 | 0 | 0 | 0 | Completed
E-Proc-Cycle2 | 11 Apr 2021 | 44 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | Completed(Note: Requisition approval workflow is considered for next PI as there are design-changes)
AP-Cycle2 | 11 Apr 2021 | 419 | 29 | 448 | 395 | 359 | 41 | 48 |  | In China instance CNFUSYS1, we are waiting for the refresh to continue further. Taiwan batch execution verification is currently in progress.

## Slide 17: Execution Tracker for S2P
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
IND | Purchasing | Automation | Regression | Cycle 2 | Bhanu | Data Input | 8-Mar-21 | 8-Mar-21 | 8-Mar-21 | 8-Mar-21
 |  |  |  |  |  | Batch | 9-Mar-21 | 9-Mar-21 | 9-Mar-21 | 9-Mar-21
 |  |  |  |  |  | Verification | 10-Mar-21 | 10-Mar-21 | 10-Mar-21 | 10-Mar-21
 |  |  |  |  |  | Re-run | 11-Mar-21 | 11-Mar-21 | 11-Mar-21 | 11-Mar-21
IND | AP | Automation | Regression | Cycle 2 | Aishwarya | Data Input | 12-Mar-21 | 12-Mar-21 | 12-Mar-21 | 12-Mar-21
 |  |  |  |  |  | Batch | 15-Mar-21 | 15-Mar-21 | 15-Mar-21 | 15-Mar-21
 |  |  |  |  |  | Verification | 16-Mar-21 | 16-Mar-21 | 16-Mar-21 | 16-Mar-21
 |  |  |  |  |  | Re-run | 17-Mar-21 | 17-Mar-21 | 16-Mar-21 | 16-Mar-21
JPN | AP | Automation | Regression | Cycle 2 | Nazeer | Data Input | 18-Mar-21 | 18-Mar-21 | 18-Mar-21 | 18-Mar-21
 |  |  |  |  |  | Batch | 19-Mar-21 | 19-Mar-21 | 19-Mar-21 | 19-Mar-21
 |  |  |  |  |  | Verification | 21-Mar-21 | 21-Mar-21 | 19-Mar-21 | 19-Mar-21
 |  |  |  |  |  | Re-run | 22-Mar-21 | 22-Mar-21 | 22-Mar-21 | 22-Mar-21

## Slide 18: Projection for next 2 weeks..contd
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
LAOS | AP | Automation | Regression | Cycle 2 | Bhanu | Data Input | 23-Mar-21 | 23-Mar-21 | 18-Mar-21 | 22-Mar-21
 |  |  |  |  |  | Batch | 24-Mar-21 | 24-Mar-21 | 23-Mar-21 | 23-Mar-21
 |  |  |  |  |  | Verification | 25-Mar-21 | 25-Mar-21 | 24-Mar-21 | 25-Mar-21
 |  |  |  |  |  | Re-run | 26-Mar-21 | 26-Mar-21 | 26-Mar-21 | 26-Mar-21
TWN | AP | Automation | Regression | Cycle 2 | Kritika&Nazeer | Data Input | 29-Mar-21 | 29-Mar-21 | 29-Mar-21 | 29-Mar-21
 |  |  |  |  |  | Batch | 30-Mar-21 | 30-Mar-21 | 30-Mar-21 | 30-Mar-21
 |  |  |  |  |  | Verification | 31-Mar-21 | 31-Mar-21 | 31-Mar-21 | 
 |  |  |  |  |  | Re-run | 01-Apr-21 | 01-Apr-21 |  | 
CHN | AP | Automation | Regression | Cycle 2 | Swati | Data Input | 02-Apr-21 | 02-Apr-21 | 24-Mar-21 | 
 |  |  |  |  |  | Batch | 05-Apr-21 | 05-Apr-21 |  | 
 |  |  |  |  |  | Verification | 06-Apr-21 | 06-Apr-21 |  | 
 |  |  |  |  |  | Re-run | 07-Apr-21 | 07-Apr-21 |  | 
AUS | AP | Manual | Regression | Cycle2 | Bhanu,Swati & Aishwarya | Execution | 08-Apr-21 | 10-Apr-21 | 22-Mar-21 | 

## Slide 19: On – Going Tracking
Initiative Name | Current Status | Confluence link
Implementation of good practices. Draft V1. | Document available in confluence page | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK
Module for maintaining login credentials | Working as expected | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK