## Slide 1: PeopleSoft Automation
Participants : Sameer Khanna, Kathy Kha, Sidhant Dayal, Vineet Wadwekar, Shivangi Tyagi, Venkat P, Karthik R, Sourav Mitra, Shyam Jha, Ramesh N, Navneet Jha, Bhanu M and Jatin P.

## Slide 2: Automation Status as on 23rd Dec 2020
Focus Area | Regression Test Cases – As on 23rd Dec |  | Progression Automation – Identified in Sprint 1 |  | Comment
 | Total | Verified / Working | Automatable | Automated | 
HCM | 305 | 305 | 6 | 6 | Existing 4 test cases were used for progression testing.
GL | 422 | 422 |  |  | 
AM | 238 | 238 |  |  | 
LA | 78 | 78 |  |  | 
AP | 419 | 419 |  |  | 
Purchasing | 95 | 95 |  |  | 
E-Proc | 44 | 44 |  |  | 

## Slide 3: Execution Status as on 23rd Dec 2020
Focus Area | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Automated | Manual | Total Regression test cases | Executed till 23th Dec | Pass | Fail | Not Executed | Defect Resolved | ETA
GL - Cycle 1 | 422 | 34 | 456 | 451 | 450 | 1 | 5 | 40 out of 42 | Completed except for 5 Manual Test cases related archival are deferred to PT upgrade (ETA 20th Feb) and 1 failed test case.
GL – Cycle 2 | 422 | 34 | 456 | 80 | 39 | 41 | 376 | 0 out of 1 | ETA : 25th Jan. Parameter’s are not matching and unexpected error in QA Environment.
AM –Cycle 1 | 238 | 18 | 256 | 256 | 256 | 0 | 0 | 3 out of 3 | Completed.
AM-Cycle 2 | 238 | 18 | 256 | 72 | 63 | 9 | 184 | 0 | ETA : 25th Jan. Parameter’s are not matching and unexpected error in QA Environment.

## Slide 4: Execution Status as on 23rd Dec 2020
Focus Area | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Automated | Manual | Total Regression test cases | Executed till 23rd Dec | Pass | Fail | Not Executed | Defect Resolved | ETA
LA –Cycle 1 | 78 | 0 | 78 | 75 | 75 | 0 | 3 | 0 | Completed, except for 3 Test cases which are archival are deferred due to dependency on upgraded PeopleTools instance (ETA : 31st Jan)
LA- Cycle 2 | 78 | 0 | 78 | 0 | 0 | 0 | 78 | 0 | ETA – 25th Jan
AP | 419 | 26 | 445 | 445 | 427 | 18 | 0 | 1 out of 1 | ETA :24th Dec.
Purchasing | 95 | 0 | 95 | 95 | 95 | 0 | 0 | 0 | Completed.
E-Proc | 44 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | Completed.

## Slide 5: Execution Status graphical representation
Chart: Execution Status
| GL - Cycle 1 | GL – Cycle 2 | AM –Cycle 1 | AM-Cycle 2 | LA –Cycle 1 | LA- Cycle 2 | AP | Purchasing | E-Proc
Automated | 422 | 422 | 238 | 238 | 78 | 78 | 419 | 95 | 44
Manual | 34 | 34 | 18 | 18 | 0 | 0 | 26 | 0 | 0
Total Regression test cases | 456 | 456 | 256 | 256 | 78 | 78 | 445 | 95 | 44
Executed till 23th Dec | 451 | 80 | 256 | 72 | 75 | 0 | 445 | 95 | 44
Pass | 450 | 39 | 256 | 63 | 75 | 0 | 427 | 95 | 44
Fail | 1 | 41 | 0 | 9 | 0 | 0 | 18 | 0 | 0
Not Executed | 5 | 376 | 0 | 184 | 3 | 78 | 0 | 0 | 0

## Slide 6: Execution Status as on 9th Dec 2020
Focus Area | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Total Regression test cases | Automated | Manual | Executed till 9th Dec | Pass | Fail | Not Executed | Defect Resolved | ETA
HCM | 305 | 305 | 0 | 270 | 250 | 20 | 35 | 0 | Batch execution is working as expected. Ready to be executed every sprint.
GL | 449 | 415 | 34 | 407 | 384 | 23 | 42 | 27 out of 29 | ETA : ST / regression by 15th Dec.
AM | 256 | 238 | 18 | 256 | 256 | 0 | 0 | 3 out of 3 | Completed.
LA | 78 | 54 | 0 | 54 | 54 | 0 | 24 | 0 | ETA : ST / regression by 24h Dec, added 2 more countries
AP | 445 | 419 | 26 | 363 | 307 | 56 | 82 | 0 | ETA :11th Dec. We are yet to run the batch for Vietnam and China.
Purchasing | 95 | 95 | 0 | 95 | 88 | 7 | 0 | 0 | ETA : 11th dec. Failed test cases will be re executed
E-Proc | 44 | 44 | 0 | 44 | 41 | 3 | 0 | 0 | ETA : 11th dec. Failed test cases will be re executed

## Slide 7: Blocker & Environment issue
Sl No | Backlog / Issue | Raised On | Owner | Status | Comment
1 | Environment issue . Defect Id – COFES- 461 SSL error while running PTF batch | 28th Oct | Madhav M | Open | Raised SR with Oracle, Madhav is following up. 23/12 – Under observation
2 | Environment issue . Defect Id – COFES-602 Page Getting Expired while trying to Create Journals - CNFUSYS1 | 30th Nov 20 | Madhav | Open | 
3 | Environment issue: Raised an Incident (INC3257067) when we trigger the PTF batch, it was throwing up an error pop-up which says a problem establishing secure channel for SSL/TLS with authority. | 10th Dec 20 | Neelmani Singh | Closed | 
4 | Environment issue . Excel Utility for batch file generation not working in all VM’s | 21th Dec | Infrastructure team | Open | Identified the issue and working with the Infra team. This will be taken care on all upgraded VM’s
5 | Environment issue . Upgrade of VM’s to windows 2016 and installation of MS Office 2010/2013 | 21th Dec | Infrastructure team | Open | Submitted request for upgrading four VM’s to Win 2016 and installation of MS office.

## Slide 8: On – Going Tracking
Initiative Name | Current Status | Confluence link
Implementation of good practices. Draft V1. | Document available in confluence page | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK
Module for maintaining login credentials | Working as expected | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK