## Slide 1: PeopleSoft Automation
Participants : Sameer Khanna, Sidhant Dayal, Vineet Wadwekar, Shivangi Tyagi, Karthik R, Sourav Mitra, Shyam Jha, Ramesh N, Navneet Jha, Bhanu M and Jatin P.

## Slide 2: Automation Status as on 25th Nov 2020
Focus Area | Regression Test Cases – Pre PPO |  |  | Test Cases Post PPO |  | On Going |  | Comment
 | Total | Verified / Working | Not Verified | Automatable | Automated | Progression Automation | Total | ETA
HCM | 250 | 250 | 0 | 50 | 50 | 5 | 305 | 
GL | 375 | 375 | 0 | 23 | 23 | 17 | 415 | 
AM | 238 | 238 | 0 | 0 | 0 | 0 | 238 | 
LA | 28 | 28 | 0 | 0 | 0 | 0 | 28 | 
AP | 369 | 369 | 0 | 50 | 50 | 0 | 419 | 
Purchasing | 65 | 65 | 0 | 10 | 10 | 20 | 95 | 
E-Proc | 36 | 36 | 0 | 8 | 2 | 0 | 44 | This will be completed by the end of this week . Expecting to run another batch cycle with progression scenarios included.

## Slide 3: Execution Status as on 25th Nov 2020
Focus Area | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Total Regression test cases | Automated | Manual | Executed till 25th Nov | Pass | Fail | Not Executed | Defect Resolved | ETA
HCM | 305 | 305 | 0 | 38 | 31 | 7 | 267 | 0 | ETA: First executed on 25 Nov through batch. Planning to execute all using batch by 2 Dec. Failures are being analyzed
GL | 449 | 415 | 34 | 361 | 277 | 84 | 88 | 17 out of 22 | ETA : ST / regression by 11th Dec.
AM | 256 | 238 | 18 | 222 | 222 | 0 | 34 | 3 out of 3 | ETA : ST / regression by 11th Dec.
LA | 28 | 28 | 0 | 23 | 23 | 0 | 5 | 0 | ETA : ST / regression by 11th Dec
AP | 445 | 419 | 26 | 149 | 125 | 24 | 296 | 0 | ETA : ST / regression by 11th Dec.
Purchasing | 95 | 95 | 0 | 34 | 30 | 4 | 61 | 0 | ETA : ST / regression by 11th Dec.
E-Proc | 44 | 44 | 0 | 38 | 35 | 3 | 6 | 0 | ETA : ST / regression by 11th Dec.

## Slide 4: Execution Status graphical representation
Chart: 
| HCM | GL | AM | LA | AP | Purchasing | E-Proc
Total Regression test cases | 305 | 449 | 256 | 28 | 445 | 95 | 44
Automated | 305 | 415 | 238 | 28 | 419 | 95 | 44
Manual | 0 | 34 | 18 | 0 | 26 | 0 | 0
Executed | 39 | 361 | 222 | 23 | 149 | 34 | 38
Pass | 27 | 277 | 222 | 23 | 125 | 30 | 35
Fail | 12 | 84 | 0 | 0 | 24 | 4 | 3
Not Executed | 266 | 88 | 34 | 5 | 296 | 61 | 6
Defect Raised | 0 | 19 | 3 | 0 | 0 | 0 | 0

## Slide 5: Execution Status – Automation, as on 25th Nov 2020
Focus Area | Regression Test Cases |  |  |  |  |  | Comment
 | Automated Regression test cases | Executed till 25th Nov | Pass | Fail | Not Executed | Defect Resolved | ETA
HCM | 305 | 38 | 31 | 7 | 267 | 0 | ETA: First executed on 25 Nov through batch. Planning to execute all using batch by 2 Dec. Failures are being analyzed
GL | 415 | 336 | 254 | 82 | 79 | 9 out of 13 | ETA : ST / regression by 11th Dec.
AM | 238 | 222 | 222 | 0 | 34 | 3 out 3 | ETA : ST / regression by 11th Dec.
LA | 28 | 23 | 23 | 0 | 5 | 0 | ETA : ST / regression by 11th Dec.
AP | 419 | 123 | 99 | 24 | 296 | 0 | ETA : ST / regression by 11th Dec.
Purchasing | 95 | 34 | 30 | 4 | 61 | 0 | ETA : ST / regression by 11th Dec.
E-Proc | 44 | 38 | 35 | 3 | 6 | 0 | ETA : ST / regression by 11th Dec.

## Slide 6: Execution Status – Manual, as on 25th Nov 2020
Focus Area | Regression Test Cases |  |  |  |  |  | Comment
 | Manual Regression test cases | Executed till 25th Nov | Pass | Fail | Not Executed | Defect Resolved | ETA
HCM | 0 | 0 | 0 | 0 | 0 | 0 | 
GL | 34 | 25 | 23 | 2 | 9 | 8 out of 9 | ETA : ST / regression by 11th Dec.
AM | 18 | 18 | 18 | 0 | 0 | 0 | ETA : ST / regression by 11th Dec.
LA | 0 | 0 | 0 | 0 | 0 | 0 | ETA : ST / regression by 11th Dec.
AP | 26 | 26 | 26 | 0 | 0 | 0 | ETA : ST / regression by 11th Dec.
Purchasing | 0 | 0 | 0 | 0 | 0 | 0 | ETA : ST / regression by 11th Dec.
E-Proc | 0 | 0 | 0 | 0 | 0 | 0 | ETA : ST / regression by 11th Dec.

## Slide 7: On – Going Tracking
Initiative Name | Current Status | Confluence link
Implementation of good practices. Draft V1. | Document available in confluence page | https://confluence.service.anz/pages/viewpage.action?spaceKey=CEE&title=PeopleSoft+Test+Automation
Module for maintaining login credentials | Working as expected | https://confluence.service.anz/pages/viewpage.action?spaceKey=CEE&title=PeopleSoft+Test+Automation
Test Case execution approach in Batch | Implemented for all | https://confluence.service.anz/pages/viewpage.action?spaceKey=CEE&title=PeopleSoft+Test+Automation
Export / Import Excel approach for individual test case | Implemented for all | https://confluence.service.anz/pages/viewpage.action?spaceKey=CEE&title=PeopleSoft+Test+Automation

## Slide 8: Automation Status, as on 17th Nov 2020
Focus Area | Regression Test Cases |  |  | Post PPO - Gap |  | On Going | Comment
 | Total | Verified / Working | Not Verified | Automatable | Automated | Progression Automation | ETA
HCM | 250 | 250 | 0 | 50 | 50 | 5 | 
GL | 375 | 375 | 0 | 23 | 23 | 2 | Global test cases were reported earlier as individual test cases for each country.
AM | 238 | 238 | 0 | 0 | 0 | 0 | 16 test cases were added to existing list of 222.
LA | 28 | 28 | 0 | 0 | 0 | 0 | 
AP | 369 | 369 | 0 | 10 | 10 | 0 | 
Purchasing | 65 | 65 | 0 | 10 | 10 | 4 | 
E-Proc | 36 | 36 | 0 | 8 | 0 | 0 | Post PPO - 29/11/2020(Starts in Sprint6)