## Slide 1: PeopleSoft Automation
Participants : Sameer Khanna, Kathy Kha, Sidhant Dayal, Vineet Wadwekar, Shivangi Tyagi, Venkat P, Karthik R, Sourav Mitra, Shyam Jha, Ramesh N, Bhanu M and Jatin P.

## Slide 2
PeopleSoft HCM

## Slide 3
Summary – Regression Suite
Total Regression Test Cases
. Automated : 325
. Manual : 175
Sprint 3 Update
. Total Tests : 89
. Manual Test: 37
. Reused existing automated tests : 50
. Automated/Automatable : 2/2
Team Commentary
Achievements from the past fortnight
ST for Sprint 3 stands at approx. 50% completion.
Comment on Summary – Regression Suite section
.Regression Testing for the Sprint 3 has been planned to run on 29/04/2021.
Progression testing is in progress.
Comment on the Test Execution Plan vs Actual variance
. N/A
Actions & Support
Support Needed
No open incidents or requests
Actions from previous meeting
N/A
Executive Summary for Core HR
Current area of focus:
System testing is currently underway. We have used existing PTF scripts to create test data for current sprint, as the testing in current Sprint involved Mail Notification verification, Report verification and IB messages verification.
Current status of the focus area: Green/Amber/Red
GREEN
Team
Jatin (Presenter)
John
From Core HR
Date: 29 Apr 2021

## Slide 4
PeopleSoft Core Finance- GL | AM |LA

## Slide 5
Summary – Regression Suite
Total Regression Test Cases
. Automated : 831
. Manual: 112
Progression Automation for
Corp X PI XI Sprint 3
. Total Tests : 15
. Reused existing automated tests : 0
. Automated/Automatable : 3/3
- Manual : 12
Team Commentary
Achievements from the past fortnight
Cycle 3 ST completed for China, ST for Global to commence today.
Comment on Summary – Regression Suite section
.12 tests were run manually which include Excel loaders and file verification
Comment on the Test Execution Plan vs Actual variance
. Variance due to delay in Environment readiness
Comment on the defect distribution numbers
. There is only 2 outstanding defects for China and 1 for Archival
.
Actions & Support
Support Needed
INC3268563,INC3666177 and COFES-812
Actions from previous meeting
China Online Journal Edit performance
Executive Summary for GL, AM & LA
Current area of focus: PeopleTools upgrade + GL selective adoption initiative.
System testing cycle 3 is currently underway. Cycle 1 has been completed on a lower version of tools and now closed. Cycle 2 testing was carried out in upgraded version and stands at 100% completion. Cycle 3 testing is in progress and expected to complete by 21st May.
Current status of the focus area: Green/Amber/Red
GREEN
Chart: 
| GL-CN | AM-CN | LA-CN | GL-AU
Script/Data | 1 | 3 | 0
Functional Defect | 6 | 2 | 2
Environment | 1 | 0 | 0
Chart: 
| 44296 | 44301 | 44306 | 44314 | 44323 | 44330 | 44337 | 44344
Planned Test Execution | 0 | 40 | 158 | 337 | 622 | 852 | 943
Actual Test Execution | 0 | 35 | 139 | 202
Column1
Column2
Column3
Column4
Team
Navneet (Presenter)
Ramesh
Santosh
Vishnu
Kiran
Harika
From Evolve & Protect
Date: 29 April 2021

## Slide 6
Chart: 
| 44127 | 44141 | 44155 | 44169 | 44183 | 44196
Planned Test Execution | 0 | 209 | 579 | 776
Actual Test Execution | 0 | 147 | 295 | 499 | 761 | 770
Column1
Column2
Column3
Column4
Chart: 
| GL-AU | GL-NZ | GL-UK | GL-SG | GL-HK | GL-FJ | GL-CH | AM-NZ | AM-UK | AM-CH
Script/Data | 30 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 11 | 5
Functional Defect | 17 | 2 | 2 | 3 | 2 | 1 | 5 | 2 | 1 | 1
Environments | 5 | 0 | 0 | 0 | 0 | 5 | 1 | 1 | 1 | 1

## Slide 7
Chart: 
| 44232 | 44246 | 44260 | 44274 | 44288 | 44302 | 44316
Planned Test Execution | 0 | 63 | 397 | 672 | 816 | 943
Actual Test Execution | 35 | 57 | 232 | 684 | 787 | 933
Column1
Column2
Column3
Column4
Chart: 
| GL-AU | GL-NZ | GL-UK | GL-SG | GL-HK | GL-FJ | GL-CH | AM-AU | AM-NZ | AM-CH
Script/Data | 8 | 16 | 17 | 13 | 16 | 1 | 18 | 1 | 0 | 12
Functional Defect | 5 | 2 | 1 | 0 | 1 | 0 | 7 | 0 | 0 | 7
Environments | 15 | 0 | 1 | 0 | 0 | 0 | 3 | 2 | 2 | 0

## Slide 8: Cycle 3 Execution Summary for PS GL/AM/LA
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 28h Apr | Pass | Fail | Not Executed | Defect Resolved | ETA
GL | 21st May | 422 | 42 | 464 | 96 | 93 | 3 | 0 | 6 out of 9 | 
AM | 14th-May | 238 | 70 | 308 | 68 | 68 | 0 | 0 | 2 out of 2 | 
LA | 21st-May | 171 | 0 | 171 | 43 | 43 | 0 | 0 | 2 out of 2 | 
Archival | 7th May | 11 | 0 | 11 | 7 | 7 | 2 | 0 | 1 out of 3 | 

## Slide 9: Projection for Next 2 weeks – GL/AM/LA
Country | Module | Category | Coverage | Test Cycle | Assignee | Activity | Planned Start Date | Planned End Date | Test Cases
AUS | AM | Automated | Regression | Cycle 3 | Ramesh | Execution | 21-Apr-21 | 23-Apr-21 ETA-30 Apr | 35
NZL | AM | Automated | Regression | Cycle 3 | Ramesh | Execution | 29-Apr-21 | 03-May-21 | 35
GBR | AM | Automated | Regression | Cycle 3 | Ramesh | Execution | 04-May-21 | 05-May-21 | 35
SGP | AM | Automated | Regression | Cycle 3 | Ramesh | Execution | 06-May-21 | 07-May-21 | 35
HKG | AM | Automated | Regression | Cycle 3 | Ramesh | Execution | 10-May-21 | 11-May-21 | 35
FJI | AM | Automated | Regression | Cycle 3 | Ramesh | Execution | 12-May-21 | 13-May-21 | 35
AUS | AM | Manual | Progression | Cycle 3 | Navneet | Execution | 30-Apr-21 | 06-May-21 | 19
AUS | GL | Automated | Regression | Cycle 3 | Vishnu | Execution | 29-Apr-21 | 03-May-21 | 84
NZL | GL | Automated | Regression | Cycle 3 | Vishnu | Execution | 04-May-21 | 06-May-21 | 54
SGP | GL | Automated | Regression | Cycle 3 | Vishnu | Execution | 7-May-21 | 11-May-21 | 48
GBR | GL | Automated | Regression | Cycle 3 | Vishnu | Execution | 12-Apr-21 | 13-Apr-21 | 40

## Slide 10: Projection for Next 2 weeks – GL/AM/LA
Country | Module | Category | Coverage | Test Cycle | Assignee | Activity | Planned Start Date | Planned End Date | Test Cases
GBL | Archival | Manual | Regression | Cycle 3 | Yamini | Execution | 12-Apr-21 | 23-Apr-21 ETA -7 May | 22
HKG | LA | Automated | Regression | Cycle 3 | Santosh | Execution | 29-Apr-21 | 06-May-21 | 43
SGP | LA | Automated | Regression | Cycle 3 | Vishnu | Execution | 07-May-21 | 14-May-21 | 43
AUS | AM | Manual | Regression | Cycle 3 | Yamini | Execution | 05-May-21 | 13-May-21 | 17
IB | GLOBAL | SIT | Regression | Cycle 3 | Navneet | Execution | 05-May-21 | 13-May-21 | 12

## Slide 11: Blocker & Environment issue – GL/AM/LA
Sl No | Backlog / Issue | Raised On | Owner | Status | Aging | Comment
1 | INC3268563 – Long running Online Journal Edit in China | 14th Dec 21 | Kiran | Testing completed | 83 | Build completed for EOD update changes, Unit test is in progress.
2 | INC3666177 - App Engine PSARCHIVE is running long in GBFAUQA1 | 21st Apr 21 | Yamini | Open | 7 | DB team working on it
3 | COFES-812 Data in all triggers in missing in CNFUSYS1 | 26th Apr 21 | Ajal | Open | 4 | 
4 | INC3657727 – GLPCLOSE running to error in China | 19th Apr 21 | Vishnu | Closed | 5 | 

## Slide 12: Cycle 1 Execution Summary for PS GL
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 31st Mar | Pass | Fail | Not Executed | Defect Resolved | ETA
GL - Cycle 1 | 25 Dec 2020 | 422 | 34 | 456 | 451 | 451 | 0 | 5 | 42 out of 42 | Completed except for 5 Manual Test cases related archival are deferred to Cycle 3 (ETA 11thh Apr) and 1 failed test case.
AM –Cycle 1 | 25 Dec 2020 | 238 | 18 | 256 | 256 | 256 | 0 | 0 | 3 out of 3 | Completed.
LA –Cycle 1 | 25 Dec 2020 | 78 | 0 | 78 | 78 | 78 | 0 | 0 | 0 | Completed.

## Slide 13
Source to Pay (S2P)

## Slide 14
Summary – Regression Suite
Total Regression Test Cases
. Automated (AP/Purchasing/E-Proc) : 446 & 95 & 44(Total of 558)
. Manual(AP/Purchasing): 30 & 4(Total of 34)
Progression Automation for
Corp X PI XI Sprint 3
. Total Tests : 89
Manual Tests : 76
. Reused existing automated tests : 3
. Automated/Automatable : 7/10
Team Commentary
Achievements from the past fortnight
. Completed AP test execution for China failed Scenarios; Manual scenarios execution got completed including the re-testing of 10 scenarios. Data Input for AP_IND is completed.
.Ariba OK2PAY file integration testing is Completed Successfully.
Comment on Summary – Regression Suite section
. AP Batch results for India is yet to be analyzed.
Comment on the Test Execution Plan vs Actual variance
. Due to SIT test Execution & China UAT Support, we are deviated by 2 days. Hopefully, we will cover this difference in the next 2 weeks.
Comment on the defect distribution numbers
.PR/Voucher approval users list page issue is fixed now and retest Succeded.
Actions & Support
Support Needed
.SIT is in progress in which we are yet to receive confirmation from AML NetReveal team on when they can receive the files and confirm us back.
.HCM-FMS integration got some issue with connectivity as FMS is unable to receive the triggered transactions. Chaitanya is supporting us on this task alongside Jatin.
Executive Summary for Bhanu
Current area of focus: People Tools upgrade + GL selective adoption initiative.
System testing cycle 3 is currently underway. Cycle 1 has been completed on a lower version of tools and now closed. Cycle 2 testing has been Completed in Upgraded version of tools and now closed. Cycle 3 testing is Currently in progress and is planned to complete on 14th May 2021.
Current status of the focus area: Green/Amber/Red
Green
Chart: 
| Thailand | UK | Taiwan | China
Script/Data | 0 | 0 | 9 | 0
Functional Defect | 1 | 1 | 0 | 1
Environment | 0 | 0 | 0 | 0
Intermittent Issue | 0 | 0 | 0 | 0
Chart: 
| 44301 | 44302 | 44305 | 44306 | 44307 | 44308 | 44309 | 44312 | 44313
Planned Test Execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44
Actual Test Execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Column1
Column2
Column3
Column4
Team
Bhanu (Presenter)
Aishwarya
Swati
Nazeer
Kritika
From S2P Squad
Date: 29 April 2021

## Slide 15
Chart: 
| 23 Oct - AU | 30 Oct - AU | 6 Nov - NZL | 13 Nov - NZL | 20 Nov - SGP | 27 Nov - JPN | 4 Dec - TWN | 8 Dec - LAOS | 11 Dec - IND | 18 Dec - VNM | 25 Dec - CHN | 31 Dec - CHN
Planned Test Execution | 20 | 21 | 39 | 39 | 41 | 41 | 40 | 41 | 85 | 40 | 17 | 18
Actual Test Execution | 18 | 23 | 38 | 40 | 38 | 41 | 39 | 36 | 83 | 40 | 15 | 18
Column1
Column2
Column3
Column4
Chart: 
| AP | PUR | E-PROC
Functional/Scripts | 1 | 0 | 0
Environment | 0 | 0 | 0
Intermittent | 0 | 0 | 0
Build issue | 1 | 0 | 0

## Slide 16
Chart: 
| 44286 | 44287 | 44288 | 44291 | 44292 | 44293 | 44294 | 44295
Planned Test Execution | 0 | 9 | 6 | 27 | 0 | 6 | 15 | 18
Actual Test Execution | 6 | 19 | 16 | 6 | 18 | 9 | 27 | 4
Column1
Column2
Column3
Column4
Chart: 
| Thailand | UK | Taiwan | China
Script/Data | 0 | 0 | 9 | 0
Functional Defect | 1 | 1 | 0 | 1
Environment | 0 | 0 | 0 | 0
Intermittent Issue | 0 | 0 | 0 | 0

## Slide 17: Cycle 2 Execution Summary for S2P
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 17th Mar | Pass | Fail | Not Executed | Defect Resolved | ETA
Purchasing-Cycle2 | 5 Mar 2021 | 95 | 0 | 95 | 95 | 95 | 0 | 0 | 0 | Completed
E-Proc-Cycle2 | 11 Apr 2021 | 44 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | Completed(Note: Requisition approval workflow is considered for next PI as there are design-changes)
AP-Cycle2 | 11 Apr 2021 | 419 | 29 | 448 | 448 | 448 | 0 | 0 | 3 of 3 | Taiwan execution is completed successfully. China Execution is completed successfully after the re-testing of the failed scenarios went well forward.

## Slide 18: Cycle 3 Execution Summary for S2P
Focus Area |  | Regression Test Cases |  |  |  |  |  |  |  | Comment
 | Planned End Date | Automated | Manual | Total Regression test cases | Executed till 28th Apr | Pass | Fail | Not Executed | Defect Resolved | ETA
Purchasing-Cycle3 | 7 May 2021 | 65 | 4 | 69 | 0 | 0 | 0 | 69 | 0 | 
E-Proc-Cycle3 | 28 Apr 2021 | 44 | 0 | 44 | 0 | 0 | 0 | 44 | 0 | ETA:30th Apr 2021
AP-Cycle3 | 14 May 2021 | 41 | 14 | 55 | 0 | 0 | 0 | 55 | 0 | 

## Slide 19: Execution Tracker for S2P
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
IND | Purchasing | Automation | Regression | Cycle 2 | Bhanu | Data Input | 8-Mar-21 | 8-Mar-21 | 8-Mar-21 | 8-Mar-21
 |  |  |  |  |  | Batch | 9-Mar-21 | 9-Mar-21 | 9-Mar-21 | 9-Mar-21
 |  |  |  |  |  | Verification | 10-Mar-21 | 10-Mar-21 | 10-Mar-21 | 10-Mar-21
 |  |  |  |  |  | Re-run | 11-Mar-21 | 11-Mar-21 | 11-Mar-21 | 11-Mar-21
IND | AP | Automation | Regression | Cycle 2 | Aishwarya | Data Input | 12-Mar-21 | 12-Mar-21 | 12-Mar-21 | 12-Mar-21
 |  |  |  |  |  | Batch | 15-Mar-21 | 15-Mar-21 | 15-Mar-21 | 15-Mar-21
 |  |  |  |  |  | Verification | 16-Mar-21 | 16-Mar-21 | 16-Mar-21 | 16-Mar-21
 |  |  |  |  |  | Re-run | 17-Mar-21 | 17-Mar-21 | 16-Mar-21 | 16-Mar-21
JPN | AP | Automation | Regression | Cycle 2 | Nazeer | Data Input | 18-Mar-21 | 18-Mar-21 | 18-Mar-21 | 18-Mar-21
 |  |  |  |  |  | Batch | 19-Mar-21 | 19-Mar-21 | 19-Mar-21 | 19-Mar-21
 |  |  |  |  |  | Verification | 21-Mar-21 | 21-Mar-21 | 19-Mar-21 | 19-Mar-21
 |  |  |  |  |  | Re-run | 22-Mar-21 | 22-Mar-21 | 22-Mar-21 | 22-Mar-21

## Slide 20: Execution Tracker for S2P
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
LAOS | AP | Automation | Regression | Cycle 2 | Bhanu | Data Input | 23-Mar-21 | 23-Mar-21 | 18-Mar-21 | 22-Mar-21
 |  |  |  |  |  | Batch | 24-Mar-21 | 24-Mar-21 | 23-Mar-21 | 23-Mar-21
 |  |  |  |  |  | Verification | 25-Mar-21 | 25-Mar-21 | 24-Mar-21 | 25-Mar-21
 |  |  |  |  |  | Re-run | 26-Mar-21 | 26-Mar-21 | 26-Mar-21 | 26-Mar-21
TWN | AP | Automation | Regression | Cycle 2 | Kritika,Bhanu&Nazeer | Data Input | 29-Mar-21 | 29-Mar-21 | 29-Mar-21 | 29-Mar-21
 |  |  |  |  |  | Batch | 30-Mar-21 | 30-Mar-21 | 30-Mar-21 | 30-Mar-21
 |  |  |  |  |  | Verification | 31-Mar-21 | 31-Mar-21 | 31-Mar-21 | 31-Mar-21
 |  |  |  |  |  | Re-run | 01-Apr-21 | 01-Apr-21 | 01-Apr-21 | 03-Apr-21
CHN | AP | Automation | Regression | Cycle 2 | Swati,Bhanu & Aishwarya | Data Input | 02-Apr-21 | 02-Apr-21 | 24-Mar-21 | 08-Apr-21
 |  |  |  |  |  | Batch | 05-Apr-21 | 05-Apr-21 | 08-Apr-21 | 08-Apr-21
 |  |  |  |  |  | Verification | 06-Apr-21 | 06-Apr-21 | 09-Apr-21 | 09-Apr-21
 |  |  |  |  |  | Re-run | 07-Apr-21 | 07-Apr-21 | 09-Apr-21 | 19-Apr-21
AUS | AP | Manual | Regression | Cycle2 | Bhanu,Swati & Aishwarya | Execution | 08-Apr-21 | 10-Apr-21 | 22-Mar-21 | 12-Apr-21

## Slide 21: Projection for next 2 weeks..contd
Country | Module | Category | Coverage | Test Cycle 2 | Assignee | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
IND | E-PROC | Automation | Regression | Cycle 3 | Bhanu | Data Input | 23-Apr-21 | 23-Apr-21 | 26-Apr-21 | 27-Apr-21
 |  |  |  |  |  | Batch | 26-Apr-21 | 26-Apr-21 | 28-Apr-21 | 
 |  |  |  |  |  | Verification | 27-Apr-21 | 27-Apr-21 |  | 
 |  |  |  |  |  | Re-run | 28-Apr-21 | 28-Apr-21 |  | 
AUS | AP | Automation | Regression | Cycle 3 | Aishwarya | Data Input | 29-Apr-21 | 29-Apr-21 |  | 
 |  |  |  |  |  | Batch | 30-Apr-21 | 30-Apr-21 |  | 
 |  |  |  |  |  | Verification | 03-May-21 | 03-May-21 |  | 
 |  |  |  |  |  | Re-run | 04-May-21 | 04-May-21 |  | 
IND | PUR | Automation | Regression | Cycle 3 | Nazeer | Data Input | 05-Apr-21 | 05-May-21 |  | 
 |  |  |  |  |  | Batch | 06-May-21 | 06-May-21 |  | 
 |  |  |  |  |  | Verification | 07-May-21 | 07-May-21 |  | 
 |  |  |  |  |  | Re-run | 10-May-21 | 10-May-21 |  | 
AUS,IND | AP | Manual | Regression | Cycle3 | Bhanu , Swati & Aishwarya | Execution | 11-May-21 | 14-May-21 |  | 

## Slide 22: Blocker & Environment issue – AP/E-Procurement/Purchasing
Sl No | Backlog / Issue | Raised On | Owner | Status | Aging | Comment
1 | Oracle SR (SR 3-25722848061) - Invalid view issue on Approver name hyper link on Payment Request Center page. | 20th Apr 21 | Nagaraju R | Closed | 6 | 
2 | REQ1763891-GBFUSUP2_PIA_ACCESS_REQUEST for missing roles | 27th Apr 21 | Chaitanya V | Closed | 2 | 
3 | REQ1750653-Request for DB access in CNFAUQA1 region | 21st Apr 21 | Lavanya C | Closed | 1 | 
4 | REQ1744961- Request to get the IB Connectivity between HCMUSYS1 and GBFAUQA1 to support SIT testing | 19th Apr 21 | Chaitanya V | Closed | 2 | 

## Slide 23: On – Going Tracking
Initiative Name | Current Status | Confluence link
Implementation of good practices. Draft V1. | Document available in confluence page | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK
Module for maintaining login credentials | Working as expected | https://confluence.service.anz/display/CEE/ANZ+PEOPLESOFT+TEST+FRAME+WORK