## Plan
Total Failed Automation Test Cases | [6 empty] | 97
Average TC Execution/Person Day | [6 empty] | 3
Dates | Test Week | Man Days Available | Planned Test Cases (per day) | Planned Test Cases (cumulative) | Failed Test Cases incl Blocked | Failed Test Cases (cumulative) | Actual Executed Test Cases incl NA (per day) | Actual Executed Test Cases (cumulative) | Difference in Test Execution | Cumulative Difference in Test Execution | Planned Test Execution % | Actual Test Execution % | Activity
2020-08-31 | 1 | 0 | 0 | 0 | 3 | 3 |  | 0 | 0 | 0 | 0% | 0% | Holiday
2020-09-01 | 1 | 2 | 6 | 6 |  |  |  | 0 | 6 | 6 | 6.186% | 0% | Automation Script debugging / tuning
2020-09-02 | 1 | 2 | 6 | 12 | 3 | 6 |  | 0 | 6 | 12 | 12.37% | 0% | Automation Script debugging / tuning
2020-09-03 | 1 | 2 | 6 | 18 | 1 | 7 |  | 0 | 6 | 18 | 18.56% | 0% | Automation Script debugging / tuning
2020-09-04 | 1 | 2 | 6 | 24 | 10 | 17 |  | 0 | 6 | 24 | 24.74% | 0% | Automation Script debugging / tuning
2020-09-05 | 0 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 24 | 24.74% | 0%
2020-09-06 | 0 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 24 | 24.74% | 0%
2020-09-07 | 2 | 2 | 6 | 30 | 15 | 32 |  | 0 | 6 | 30 | 30.93% | 0% | Automation Script debugging / tuning
2020-09-08 | 2 | 2 | 6 | 36 | 1 | 33 |  | 0 | 6 | 36 | 37.11% | 0% | Automation Script debugging / tuning
2020-09-09 | 2 | 2 | 6 | 42 | 1 | 34 |  | 0 | 6 | 42 | 43.3% | 0% | Automation Script debugging / tuning
2020-09-10 | 2 | 2 | 6 | 48 | 4 | 38 |  | 0 | 6 | 48 | 49.48% | 0% | Automation Script debugging / tuning
2020-09-11 | 2 | 2 | 6 | 54 | 1 | 39 |  | 0 | 6 | 54 | 55.67% | 0% | Automation Script debugging / tuning
2020-09-12 | 0 | 0 | 0 | 54 |  |  | 0 | 0 | 0 | 54 | 55.67% | 0%
2020-09-13 | 0 | 0 | 0 | 54 |  |  | 0 | 0 | 0 | 54 | 55.67% | 0%
2020-09-14 | 3 | 2 | 6 | 60 | 15 | 49 |  | 0 | 6 | 60 | 61.86% | 0% | Automation Script debugging / tuning
2020-09-15 | 3 | 2 | 6 | 66 | 1 | 50 |  | 0 | 6 | 66 | 68.04% | 0% | Automation Script debugging / tuning
2020-09-16 | 3 | 2 | 6 | 72 | 1 | 51 |  | 0 | 6 | 72 | 74.23% | 0% | Automation Script debugging / tuning
2020-09-17 | 3 | 2 | 6 | 78 | 4 | 55 |  | 0 | 6 | 78 | 80.41% | 0% | Automation Script debugging / tuning
2020-09-18 | 3 | 2 | 6 | 84 | 1 | 56 |  | 0 | 6 | 84 | 86.6% | 0% | Automation Script debugging / tuning
2020-09-19 | 0 | 0 | 0 | 84 |  |  | 0 | 0 | 0 | 84 | 86.6% | 0%
2020-09-20 | 0 | 0 | 0 | 84 |  |  | 0 | 0 | 0 | 84 | 86.6% | 0%
2020-09-21 | 4 | 2 | 6 | 78 | 15 | 64 |  | 0 | 6 | 78 | 80.41% | 0% | Automation Script debugging / tuning
2020-09-22 | 4 | 2 | 6 | 84 | 1 | 65 |  | 0 | 6 | 84 | 86.6% | 0% | Automation Script debugging / tuning
2020-09-23 | 4 | 2 | 6 | 90 | 1 | 66 |  | 0 | 6 | 90 | 92.78% | 0% | Automation Script debugging / tuning
2020-09-24 | 4 | 2 | 6 | 96 | 4 | 70 |  | 0 | 6 | 96 | 98.97% | 0% | Automation Script debugging / tuning
2020-09-25 | 4 | 2 | 6 | 102 | 1 | 71 |  | 0 | 6 | 102 | 105.2% | 0% | AU AP Batch Run / Execution
2020-09-26 | 0 | 0 | 0 | 102 |  |  | 0 | 0 | 0 | 102 | 105.2% | 0% | AU e-Pro Batch Run / Execution
2020-09-27 | 0 | 0 | 0 | 102 |  |  | 0 | 0 | 0 | 102 | 105.2% | 0% | AU Purchasing Batch Run / Execution
Note on C4: Reddy, Thapovardhan: Variation in Man days due to PTO.

## Summary
Count of Test Case Name | Column Labels
Row Labels | Fail | Pass | Warning | Grand Total
Accounts Payable | 34 | 7 |  | 41
e-Procurement | 17 | 18 | 1 | 36
Purchasing | 46 | 15 | 4 | 65
Grand Total | 97 | 40 | 5 | 142

## Automation Status
Test Case Name | Module | Bug fix status | Asignee | Status | Error Message | Folder | Description | Time (in Mins) | Comment
AU_AP_VENDOR_AUDIT_REPORT | Accounts Payable |  | Aishwarya | Fail | Cannot access the component | \AUS_AUTOMATION\Accounts Payable_AUS |  | 4
AU_AP_VERIFY_ANZ_CHQ_EST_REP | Accounts Payable |  | Aishwarya | Fail | Page.Prompt: The action mode is not defined for this case. | \AUS_AUTOMATION\Accounts Payable_AUS | ANZ cheque estimation report | 2
AU_AP_VERIFY_EFT_PAYMENT | Accounts Payable |  | Aishwarya | Fail | text [Name=PYMNT_VCHR_XREF_SCHEDULED_PAY_DT$0] is display only and the value is wrong. | \AUS_AUTOMATION\Accounts Payable_AUS |  | 3
AU_AP_VERIFY_EXP_PAYMT | Accounts Payable |  | Aishwarya | Fail | Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\Accounts Payable_AUS | Verify Express Payment | 3
AU_AP_VOUCHER_AUDIT_ALL_OPERAT | Accounts Payable |  | Aishwarya | Fail | The link/button Name=CDM_WRK_INDEX_BTN$0 to sec page disabled OR sec page not recognized as one | \AUS_AUTOMATION\Accounts Payable_AUS | Vchr Audit RptAll Operators Al | 4
AU_AP_VOUCHER_AUDIT_SETID | Accounts Payable |  | Aishwarya | Fail | The link/button Name=CDM_WRK_INDEX_BTN$0 to sec page disabled OR sec page not recognized as one | \AUS_AUTOMATION\Accounts Payable_AUS | Vchr Audit Rpt All Operators V | 1
AU_AP_VOUCHER_VALIDATION_ALL | Accounts Payable |  | Aishwarya | Fail | Process anz0541a not found in Process list | \AUS_AUTOMATION\Accounts Payable_AUS | Validation All Vendor All Orig | 2
AU_AP_VOUCHER_VALIDATION_ORIGI | Accounts Payable |  | Aishwarya | Fail | Process anz0541a not found in Process list | \AUS_AUTOMATION\Accounts Payable_AUS | Voucher validation by origin | 1
AU_AP_VOUCHR_AUDIT_AL_VENDRORG | Accounts Payable |  | Aishwarya | Fail | link.Click [id=pthdr2logout];Object not found in the page, or the access is denied to the Frame. | \AUS_AUTOMATION\Accounts Payable_AUS | Vchr Audit Rpt All Operators A | 3
AU_AP_WITHOLDING_VCHR | Accounts Payable |  | Aishwarya | Fail | text.Set_Value [Name=VCHR_ADDSRCH_VW_VENDOR_ID] -> 00993654;Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\Accounts Payable_AUS | Verify Witholding voucher | 2
AU_AP__PYMNT_REGISTRY_RPT | Accounts Payable |  | Aishwarya | Fail | text.Set_Value [Name=QUERY_RUN_PARM_BNDVALUE$0] -> APAUPC;Object not found in the page, or the access is denied to the Frame. | \AUS_AUTOMATION\Accounts Payable_AUS | PAYMENT_REGISTER | 1
AU_AP_VCHRPOST_ORIGIN | Accounts Payable |  | Aishwarya | Fail | button.Click [name=#ICSearch];Msg: You are not authorized to post vouchers.(button.Click [Name=#ICSave];Msg: Highlighted fields are required. (15,30)) | \AUS_AUTOMATION\Accounts Payable_AUS | VCHR_POST_ORIGIN | 2
AU_AP_APTOGL_ENDTOEND | Accounts Payable |  | Aishwarya | Fail | button.Click [name=#ICSearch];Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\Accounts Payable_AUS | AP_TO_GL_ENDTOEND | 2
AU_AP_ASSET_VOUCHER | Accounts Payable |  | Aishwarya | Fail | button.Click [name=#ICSearch];Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\Accounts Payable_AUS | Asset Voucher multiline VAT | 2
AU_AP_CHLD_ARIBA_EXT | Accounts Payable |  | Aishwarya | Fail | link.Click [id=pthdr2logout];Object not found in the page, or the access is denied to the Frame. | \AUS_AUTOMATION\Accounts Payable_AUS | CHLD_ARIBA_EXT_PROC | 3
AU_AP_CLOSE_VOUCHER | Accounts Payable |  | Aishwarya | Fail | button.Click [name=#ICSearch];Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\Accounts Payable_AUS | Close Voucher Process | 2
AU_AP_CREATE_RUN_PYCL_EFT | Accounts Payable |  | Aishwarya | Fail | button.Click [name=#ICSearch];Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\Accounts Payable_AUS | Create&Run Paycycle_EFT | 1
AU_AP_CREATE_VENDOR_VAT | Accounts Payable |  | Aishwarya | Fail | Msg: You are not authorized to enter suppliers. Contact your system administrator. (7025,9) | \AUS_AUTOMATION\Accounts Payable_AUS | Create Vendor by VAT | 1 | Not authorized to enter suppliers with Venkat ID
AU_AP_EMPTORIS_EXTRACT | Accounts Payable |  | Aishwarya | Fail | Object not found in the page, or the access is denied to the Frame. | \AUS_AUTOMATION\Accounts Payable_AUS | Emptoris Extract | 13
AU_AP_JOURNAL_VOUCHER | Accounts Payable |  | Aishwarya | Fail | Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\Accounts Payable_AUS | Journal Voucher Creation | 1
AU_AP_MANUAL_CHK_PAYMENT | Accounts Payable |  | Aishwarya | Fail | Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\Accounts Payable_AUS | Manual check payment method | 1
AU_AP_OK2PAY_LOAD | Accounts Payable |  | Aishwarya | Fail | No Success (final status) <> success (expected status) | \AUS_AUTOMATION\Accounts Payable_AUS | ANZ_OK2PAY_LOAD | 1 | no files so process ran to no success
AU_AP_PARNT_ARIBA_EXTRCT_PRCSS | Accounts Payable |  | Aishwarya | Pass |  | \AUS_AUTOMATION\Accounts Payable_AUS | PRNT_ARIBA_EXT_PROC | 2
AU_AP_PAYMENT_CANCEL_HOLD | Accounts Payable |  | Aishwarya | Fail | Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\Accounts Payable_AUS | Payment Cancel Reopen(hold) | 1 | Ran for SGP as 05025 BU not present in the lookup
AU_AP_PAYMENT_CANCEL_NO_REISSU | Accounts Payable |  | Aishwarya | Fail | Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\Accounts Payable_AUS | Payment cancel-do not reissue | 1 | Ran for IND as 05025 BU not present in the lookup
AU_AP_PAYMENT_CANCEL_REISSUE | Accounts Payable |  | Aishwarya | Fail | Page.PromptOk: Multiple values returned after Search | \AUS_AUTOMATION\Accounts Payable_AUS | Payment Cancel Reopen(Reissue) | 5
AU_AP_PAYMENT_MANUAL_RECORD | Accounts Payable |  | Aishwarya | Fail | Msg: Payment amount must be greater than 0. (7015,73) | \AUS_AUTOMATION\Accounts Payable_AUS | Payment (Manual Record) | 2
AU_AP_PAYNT_INQRY_SEL_PAYMT_RE | Accounts Payable |  | Aishwarya | Fail | Object not found in the page, or the access is denied to the Frame. | \AUS_AUTOMATION\Accounts Payable_AUS | Payment_inqry_slctd_pymnt_Refr | 2
AU_AP_POSTED_VOUCHER_DELETION | Accounts Payable |  | Aishwarya | Pass |  | \AUS_AUTOMATION\Accounts Payable_AUS |  | 6
AU_AP_PSTD_VCHR_LIST_REP | Accounts Payable |  | Aishwarya | Fail | Process request has timed out for instance 17270445 with status PROCESSING | \AUS_AUTOMATION\Accounts Payable_AUS | PSTD_VCHR_LIST_REP | 62
AU_AP_PYMNT_HISTRY_BANK_REPORT | Accounts Payable |  | Aishwarya | Pass |  | \AUS_AUTOMATION\Accounts Payable_AUS | Payment_history_Bank | 5
AU_AP_PYMNT_TRIAL_RG_RPT | Accounts Payable |  | Aishwarya | Pass |  | \AUS_AUTOMATION\Accounts Payable_AUS | Trial Register | 5
AU_AP_PYMT_HIS_REP_BY_SUPP | Accounts Payable |  | Aishwarya | Pass |  | \AUS_AUTOMATION\Accounts Payable_AUS | PYMNT_HIS_BY_SUPPLIER | 4
AU_AP_PYT_HTRY_REPRT_BY_PAYMHD | Accounts Payable |  | Aishwarya | Pass |  | \AUS_AUTOMATION\Accounts Payable_AUS | PYMN_HIS_BY_PAY_MTHD | 40
AU_AP_UNPOST_VOUCHER_DELETION | Accounts Payable |  | Aishwarya | Pass |  | \AUS_AUTOMATION\Accounts Payable_AUS | Unpost_voucher_deletion | 10
AU_AP_UPDATE_VENDOR | Accounts Payable |  | Aishwarya | Fail | No matching values were found when attempting to Update a component | \AUS_AUTOMATION\Accounts Payable_AUS | Update Vendor Information | 10
AU_AP_VALIDATION_BY_VENR_SETID | Accounts Payable |  | Aishwarya | Fail | anz0541a not found in process list | \AUS_AUTOMATION\Accounts Payable_AUS | Validation Vendor by SetId | 3
AU_AP_VALIDATION_ORIGIN_VENDR | Accounts Payable |  | Aishwarya | Fail | Invalid value -- press the prompt button or hyperlink for a list of valid values | \AUS_AUTOMATION\Accounts Payable_AUS | Validation origin & vendor | 3
AU_AP_VAT_VOUCHER | Accounts Payable |  | Aishwarya | Fail | Invalid Supplier ID | \AUS_AUTOMATION\Accounts Payable_AUS | VAT Voucher | 5
AU_AP_VCHR_ENTRY_MUL_CURRENCY | Accounts Payable |  | Aishwarya | Fail | Object not found in the page | \AUS_AUTOMATION\Accounts Payable_AUS |  | 3
AU_AP_VENDOR_APPROVAL | Accounts Payable |  | Aishwarya | Fail | You are not authorized to approve the supplier | \AUS_AUTOMATION\Accounts Payable_AUS | Vendor Approval | 3
CREATE_REQUISITON_IND | Purchasing |  | Aishwarya | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing |  | 3
INQUIRE_ON_PO_INQUIRY_INDIA | Purchasing |  | Aishwarya | Fail | Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO INQUIRY | Inquire on Purchase Orders - P | 2
INQUIRE_ON_RECEIPT_LOC_IND_01 | Purchasing |  | Aishwarya | Fail | Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO INQUIRY | Inquire on Receipts based on L | 5
INQUIRE_ON_RECEIPT_LOC_IND_02 | Purchasing |  | Aishwarya | Fail | No parameters | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO INQUIRY | Inquire on Receipts based on L | 3
INQUIRE_RECEIPT_INDIA_01 | Purchasing |  | Aishwarya | Fail | no valid summary in worklist | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO INQUIRY | approve requisition | 2
INQUIRE_RECEIPT_INDIA_02 | Purchasing |  | Aishwarya | Fail | No buyer in the prompt in valid | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO INQUIRY | create po and receipt | 1
INQUIRE_RECEIPT_INDIA_03 | Purchasing |  | Aishwarya | Fail | Page.PromptOk: No matching values were found when attempting to Update a component | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO INQUIRY | verifying receipt status | 3
INQUIRE_RECEIPT_INDIA_SHELL | Purchasing |  | Aishwarya | Fail | Error retrieving PeopleTools Release information | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO INQUIRY | Inquire Receipt | 4
INQUIRE_RECEIPT_ON_LOC_SHELL | Purchasing |  | Aishwarya | Fail | Can't reach the Secondary Page requested [page PO_DEFAULTS] | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO INQUIRY | Inquire on Receipts based on L | 2
PO_ACTIV_REPORT | Purchasing |  | Aishwarya | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Reports | PO activity report | 3
PO_EXPEDITIN_REPORT | Purchasing |  | Aishwarya | Fail | Key: id=CDM_LIST_VW_PRCSINSTANCE [span] - Value: 17270788 | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Reports | PO Expediting report | 1
CREATE_CHANGE_ORDER_ADD_NEWLIN | Purchasing |  | Aishwarya | Fail | Fail getting status, error trying synchronization | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Maintainance | Create Change order_Add new li | 2
CREATE_CHANGE_ORD_CANCEL_INDIA | Purchasing |  | Aishwarya | Fail | Object not found in the page, or the access is denied to the Frame. | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Maintainance | CREATE_CHANGE_ORDER_CANCEL | 2
CREATE_CHANGE_ORD_CHANGE_ITEM | Purchasing |  | Aishwarya | Fail | button.Click [Name=#ICSave];Msg: Warning -- If you do not select a Purchase Order status, no PO will be printed for this run control ID. Continue? (10010,1) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Maintainance | Create Change order_Change ite | 10
CREATE_ONLINE_PO_COPY_4M_REQ | Purchasing |  | Aishwarya | Fail | SecPage: PO_DFLT_RETROFIT;Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Creation | Create Online PO copy from req | 5
CREATE_PO_INDIA | Purchasing |  | Aishwarya | Fail | SecPage: PO_DEFAULTS;Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Maintainance |  | 1
CREATE_REQUISITION | Purchasing |  | Aishwarya | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 01. Create Requisition | 3
PUR_P2P_WITH_ASS_EPRO_TILL_AM | Purchasing |  | Aishwarya | Fail | text.Set_Value [name=VCHR_ADDSRCH_VW_VENDOR_ID] -> &supplier_id;Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Processing |  | 11
PUR_PO_VO_CANNOT_BE_PAID_WO | Purchasing |  | Bhanu | Fail | link.Click [text=Select All];Object not found in the page, or the access is denied to the Frame. | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 05.PO vouchers cannot be paid | 7
PUR_RECEIPT_ACC_DETAIL_REPORT | Purchasing |  | Bhanu | Fail | combobox.Set_Value [name=PRCSRQSTDLG_WRK_SERVERNAME] -> PSUNX;combobox [name=PRCSRQSTDLG_WRK_SERVERNAME] is display only and the value is wrong. | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Reports | Receipt account detail report | 3
PUR_RECEIPT_DELIV_REPORT | Purchasing |  | Aishwarya | Warning | Scroll [1] Start: $0, Action: sel, Key: RECV_DEL; PageSave: NOT CONFIRMED | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Reports | Receipt delivery report | 3
PUR_RECEIPT_SHIP_TO_DETAI_REP | Purchasing |  | Aishwarya | Warning | Scroll [1] Start: $1, Action: sel, Key: POX5010;PageSave: NOT CONFIRMED | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Reports | Receipt Ship to detail report | 2
PUR_RECEIPT_SUMM_REPORT | Purchasing |  | Bhanu | Fail | Page.PromptOk: No matching values were found when attempting to Update a component | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Reports | Receipt Summary report | 1
PUR_REQU_TO_PO_XREF_REPORT | Purchasing |  | Aishwarya | Warning | Scroll [1] Start: $0, Action: sel, Key: POX1100;PageSave: NOT CONFIRMED | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Reports | Requisition to PO XREF Report | 3
PUR_RESUBMIT_REQUSITION | Purchasing |  | Bhanu | Fail | Verify: id=PSXLATITEM_XLATSHORTNAME [span] -> Pending;Object not found in the page, or the access is denied to the Frame. | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers |  | 2
PUR_REVIEW_CHANGE_ORDER_HISTOR | Purchasing |  | Bhanu | Fail | text.Set_Value [name=RUN_CNTL_PUR_PO_ID] -> &poid;Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Maintainance | Review Change order history | 2
PUR_RUN_PAY_CYCLE_AND_SCHEDULE | Purchasing |  | Bhanu | Fail | Object not found in the page, or the access is denied to the Frame. | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 17. Run Pay cycle and Schedule | 1
PUR_RUN_PURGE_STAGED_TABLES | Purchasing |  | Bhanu | Fail | Scroll 1. Row not Found: 16954343, 0 | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Maintainance | Run Purge staged tables proces | 2
PUR_SUBMIT_REQ_EMAIL | Purchasing |  | Aishwarya | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 03. Submit Requisition - email | 3
PUR_VERIFY_3_WAY_EXCEPTION_OV | Purchasing |  | Bhanu | Fail | Object not found, or Frame access denied | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 14. Verify 3 way exception ove | 3 | Authorization error
PUR_VERIFY_CREATION_OF_PO_VOU | Purchasing |  | Bhanu | Fail | Object not found, or Frame access denied | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 10. Verify Creation of PO Vouc | 3 | Authorization error
PUR_VERIFY_CREATION_OF_VOU_PO | Purchasing |  | Bhanu | Fail | Object not found, or Frame access denied | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 11. Verify Creation of voucher | 2 | Authorization error
PUR_VERIFY_DAM | Purchasing |  | Bhanu | Fail | Invalid value: Approval Routing | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | VERIFY_DAM | 3
PUR_VERIFY_THREE_WAY_MATCH | Purchasing |  | Bhanu | Fail | Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 13. Verify three way matching | 1
PO_ITM_CATEGORY_USAGE_REPORT | Purchasing |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Reports | PO Item category usage report | 2
PO_LISTING_REPORT | Purchasing |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Reports | PO Listings report | 2
PO_PRINT_REPORT | Purchasing |  | Bhanu | Fail | combobox [name=PRCSRQSTDLG_WRK_SERVERNAME] is display only and the value is wrong. | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Reports | Purcahse order print report | 1
PO_SCHEDULE_LISTING_REPORT | Purchasing |  | Bhanu | Fail | combobox [name=PRCSRQSTDLG_WRK_SERVERNAME] is display only and the value is wrong. | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Reports | PO Schedule listings report | 1
PO_STATUS_LISTING_REPORT | Purchasing |  | Bhanu | Fail | Scroll 1. Row not Found: 16954380 | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Reports | PO Status listings report | 2
PO_TO_REQ_XREF_REPORT | Purchasing |  | Bhanu | Fail | combobox [name=PRCSRQSTDLG_WRK_SERVERNAME] is display only and the value is wrong. | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Reports | PO to requisition XREF report | 4
PO_WITH_ATTACHMENTS_INDIA | Purchasing |  | Bhanu | Fail | Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Maintainance | PO with attachments | 2
PUR_ATTACH_SCAN_INV_TO_PO_VOU | Purchasing |  | Bhanu | Fail | Msg: Warning -- Invoice date is greater than today's date. (7030,243) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 12. Attach scanned invoice to | 13
PUR_CANCEL_DISPATCHE_PO_PARTIA | Purchasing |  | Bhanu | Fail | combobox [name=PRCSRQSTDLG_WRK_SERVERNAME] is display only and the value is wrong. | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Maintainance | Cancel a Dispatched PO that ha | 18
PUR_CANCEL_DISPATCH_PO_NOTRECE | Purchasing |  | Bhanu | Fail | Object not found in the page, or the access is denied to the Frame. | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Maintainance | Cancel a Dispatched PO that ha | 20
PUR_CREATION_OF_VOUCHER_FR_PO | Purchasing |  | Bhanu | Warning |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 11. Verify Creation of voucher | 13
PUR_DENY_REQUISITION | Purchasing |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | DENY REQUISITION | 6
PUR_DISPATCH_PURCHASE_ORDER_ON | Purchasing |  | Bhanu | Fail | Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 08. Dispatch Po EMAIL | 3
PUR_EMAIL_NOTIFY_FOR_MISSING_R | Purchasing |  | Bhanu | Fail | Msg: You are not authorized to access this component. (40,20) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 15. Email notifications for Mi | 15
PUR_GENERATE_JOURNA_ENT_FOR_PO | Purchasing |  | Bhanu | Fail | Msg: You are not authorized to access this component. (40,20) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 18. Generate Journal Entries f | 13
PUR_IND_APPROVE_A_REQUISITION | Purchasing |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers |  | 5
PUR_IND_CANCEL_SINGLE_REC_LINE | Purchasing |  | Bhanu | Fail | combobox [name=PRCSRQSTDLG_WRK_SERVERNAME] is display only and the value is wrong. | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\Receiving | Cancel single receipt line | 13
PUR_IND_CANCEL_WHOLE_RECEIPT | Purchasing |  | Bhanu | Fail | combobox [name=PRCSRQSTDLG_WRK_SERVERNAME] is display only and the value is wrong. | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\Receiving | Cancel whole receipt | 13
PUR_IND_CLOSE_A_SINGLE_RECEIPT | Purchasing |  | Bhanu | Fail | Received' (actual) <> 'Closed' (expected) | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\Receiving |  | 4
PUR_IND_CREATE_A_RECEIPT | Purchasing |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 09. Create a receipt | 10
PUR_IND_P2P_WITHOUT_ASSET_EPR | Purchasing |  | Bhanu | Fail | IRN Number field is Mandatory | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Processing |  | 3
PUR_IND_PO_CALCULATION_PRO | Purchasing |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Processing |  | 7
PUR_IND_PO_CREATE_PROCESS | Purchasing |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Processing |  | 10
PUR_IND_RECEIPT_1_LINE_PO_FULL | Purchasing |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\Receiving |  | 10
PUR_IND_RECEIPT_2_LINE_PO_FULL | Purchasing |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\Receiving |  | 10
PUR_IND_RECEPT_1_LINE_2_PO_PAR | Purchasing |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\Receiving |  | 10
PUR_IND_REJECT_RECEIVED_MATER | Purchasing |  | Bhanu | Pass | IRN Number field is Mandatory | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\Receiving | Reject received materials for | 4
PUR_IND_REJECT_RECEIVE_MATERIA | Purchasing |  | Bhanu | Fail | IRN Number field is Mandatory | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\Receiving | Reject received material credi | 3
PUR_IND_RUN_PO_RECONCILE_PRO | Purchasing |  | Bhanu | Fail | No Success | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Processing | 05 Run PO Reconcile Process | 7
PUR_IND_SOURCE_REQUISITON_TO | Purchasing |  | Bhanu | Fail | IRN Number field is Mandatory | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO Processing |  | 5
PUR_NO_MATCH_PO_VOUCHER_CANNOT | Purchasing |  | Bhanu | Fail | IRN Number field is Mandatory | \AUS_AUTOMATION\NWOW35\IND\ST\Purchasing\PO vouchers | 16. No-Match PO vouchers canno | 8
CREATE_REQUISITON | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\02.Requisition | Creating a requisition | 3
CREATE_REQ_WITH_ATTACH_COMMENT | e-Procurement |  | Bhanu | Fail | item not found | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\02.Requisition | 08.Verify Create requisition a | 2
CREATE_SPECIAL_REQ_WITH_VENDOR | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\02.Requisition | 01.Create a special request wi | 1
EPOMODIFY_AN_EXISTING_CATEGORY | e-Procurement |  | Bhanu | Fail | Scroll 1. Button not Found: Insert Row (+) | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | To modify an Existing Category | 3
EPO_PENDING_REQUISITION_MODIFY | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\03.Workflow | 13.Verify that The Pending Req | 2
EPO_REQ_SOURCE_PO_SOURCE_NOTCH | e-Procurement |  | Bhanu | Fail | Invalid value: Approval Routing | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\02.Requisition | 13.Verify that the requisition | 1
EPO_SOURCE_REQUISITON_TO_A_PO | e-Procurement |  | Bhanu | Fail | It is not possible to set the value. | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\02.Requisition | 01 Source Requisiton to a PO | 2
EPO_SOURCE_REQ_PO_EXCEPTION | e-Procurement |  | Bhanu | Fail | Object not found in the page, or the access is denied to the Frame. | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\02.Requisition | 15.Verify the Source Requisiti | 3
EPO_VERIFY_ADD_A_NEW_UOM_US | e-Procurement |  | Bhanu | Fail | button.Click [name=PV_REQ_LINE_WRK_PV_INSERT_LINE$0];Msg: Invalid Supplier ID, please check your entry. | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | 06.Verify Add a new UOM and us | 2
EPO_VERIFY_APPROVE_FISCAL_REQ | e-Procurement |  | Bhanu | Fail | link.Click [text=~*0000418874,];Object not found in the page, or the access is denied to the Frame. | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\03.Workflow | 06.Verify Approve Fiscal requi | 11
EPO_VERIFY_CANCEL_REQUISITION | e-Procurement |  | Bhanu | Fail | Scroll [1] Start: $1, Action: sel, Key: 000000000000119396;Scroll 1. Row not Found: 000000000000119396 | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\02.Requisition | Verifying cancellation of req | 5
EPO_VERIFY_CLOSE_REQUISITION | e-Procurement |  | Bhanu | Fail | Scroll [1] Start: $1, Action: sel, Key: 000000000000119396;Scroll 1. Row not Found: 000000000000119396 | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\03.Workflow |  | 9
EPO_VERIFY_CREATE_CATELOG_REQ | e-Procurement |  | Bhanu | Fail | link.Click [name=~PV_MAINNAV_HTML_PV_MANAGERLINK$*$];Object not found, or Frame access denied | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\02.Requisition | 07Verify create Catelog requis | 2
EPO_VERIFY_DENY_REQUIS_FISCAL | e-Procurement |  | Bhanu | Fail | Scroll [1] Start: $1, Action: sel, Key: 000000000000119396;Scroll 1. Row not Found: 000000000000119396 | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\03.Workflow | 08.Verify Deny Requisition at | 3
EPO_VERIFY_EDIT_REQUISITION | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\02.Requisition | 09.Verify Edit Requisition | 3
EPO_VERIFY_FUNCTIONA_ADD_BUYER | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | 14.Verify The functionality to | 2
EPO_VERIFY_FUNCTIONA_ADD_REQ | e-Procurement |  | Bhanu | Fail | Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | 13.Verify The Functionality to | 1
EPO_VERIFY_FUNCTIONA_ADD_SHIP | e-Procurement |  | Bhanu | Fail | Msg: The system does not understand the date you entered. Example date: %1 | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | 15.Verify the Functionality to | 1
EPO_VERIFY_FUNCTIONA_UPD_REQ | e-Procurement |  | Bhanu | Fail | Msg: The system does not understand the date you entered. Example date: %1 | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | 17.Verify the Functionality to | 1
EPO_VERIFY_FUNCTION_UPD_BUY | e-Procurement |  | Bhanu | Fail | Msg: Invalid value -- press the prompt button or hyperlink for a list of valid values (15,11) | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | 16.Verify the Functionality to | 1
EPO_VERIFY_INACTIVATE_ITEM | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | 07.Verify Inactivate Item | 1
EPO_VERIFY_LEVEL_1_FISCAL_APRO | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\03.Workflow | 16. Verify level 1 Fiscal appr | 4
EPO_VERIFY_LEVEL_2_FISCAL_APPR | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\03.Workflow | 17. Verify Level 2 Fiscal appr | 4
EPO_VERIFY_MODIFY_AN_ITEM_AD | e-Procurement |  | Bhanu | Warning |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | 09.Verify Modify an item by ad | 2
EPO_VERIFY_REQUI_PRINT_REPOR | e-Procurement |  | Bhanu | Fail | Condition Failed (If &var1="PDF")PDF not found | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\04.Reports | 02.Verify Requisition Print Re | 2
EPO_VERIFY_REQ_COST_DISTRIB_RE | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\04.Reports | 01.Verify Requisition cost dis | 3
EPO_VERIFY_SEARCH_CATEGORY | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | 11.Verify Search Category | 1
EPO_VERIFY_SEARCH_ITEM | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | 12.Verify Search Item | 1
EPO_VERIFY_SELF_SERVI_PAGE_REQ | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | 198.Verify The Self Service pa | 1
EPO_VERIFY_THE_FUNCTIONALI_TO | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items |  | 1
EPO_VER_SPECIA_REQ_WITHOT_VEND | e-Procurement |  | Bhanu | Fail | Approvals list need to be updated | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\02.Requisition | 06Verify Create a special requ | 2
CREATE_A_NEW_ITEM | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | Creating a new Item | 2
CREATE_A_NEW_ITEM_GROUP | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | Creating a new item group | 2
CREATE_A_NEW_ITEM_WITH_VERIFY | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | Item Verify Seatch | 3
CREATE_NEW_CATEGORY | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items\01.Create a new category | Create a new category | 2
CREATE_NEW_ITEM_FAMILY | e-Procurement |  | Bhanu | Pass |  | \AUS_AUTOMATION\NWOW35\NZL\ST\Eprocurement\Categories and Items | Creating a new item Family | 2